## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte | SM/11263 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 322/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 57.02 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte | SM/11263 | Retrofitting | Land Development at Head works site at JALGHARA Zone-X/A of Magrahat-I Block for Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I Block within "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District- South 24-Pgns." under South 24-Pgns W/S Division-I, PHE Dte. (SM/11263) | AE SWSD-II,Assistant Engineer | JE2 | ORD/000531/2024-2025 | 4077/SWD-I | 19/09/2024 | 04/10/2024 | SRIJON ENTERPRISE | 37.44 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte | SM/11263 | Retrofitting | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/A AT JALGHARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/A AT JALGHARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Total Number of FHTC ¿ 9256 Nos.) | AE SWSD-II,Assistant Engineer | JE2 | ORD/000804/2022-2023 | 3695/SWD-I | 30/03/2023 | 02/04/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1210.7 | 0 | 0 | 25
Total | [13 empty] | 1305.16 | 0 | 0