## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-VI at Sadhukhan Ardari Ektara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11264 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 322/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 56.86 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-VI at Sadhukhan Ardari Ektara mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11264 | Retrofitting | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-VI at EKTARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VI at EKTARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 9230 Nos.) | AE SWSD-II | JE2 | ORD/000373/2023-2024 | 1782/SWD-I | 11/08/2023 | 06/06/2024 | CONCORD ENGINEERING | 1862.26 | 0 | 0 | 55
Total | [13 empty] | 1919.12 | 0 | 0