## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-III at Pratapberia (Baneswarpur) mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11266 | Augmentation | Construction of 550 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Laying Distribution System and providing FHTC for Augmentation of Piped W/S Scheme of Zone-III at PRATAPBERIA (Baneswarpur) of Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 4102] [TSM/015075 & TSM/010756] | AE SWSD-II | JE2 | ORD/000073/2023-2024 | 387/SWD-I | 28/04/2023 | 02/04/2025 | PROJECT AND MAINTENANCE | 418.32 | 112.57 | 26.91 | 95
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-III at Pratapberia (Baneswarpur) mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11266 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 322/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 25.27 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-III at Pratapberia (Baneswarpur) mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11266 | Augmentation | Restoration of road from Baneswarpur Bazar to Nabin Sangha for providing 100% FHTC in Zone-III at PRATAPBERIA (Baneswarpur) of Magrahat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.- South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11266) | AE SWSD-II | JE2 | ORD/000732/2023-2024 | 437/SWD-I | 22/01/2024 | 06/02/2024 | PROJECT AND MAINTENANCE | 7.09 | 7.09 | 100 | 25
Total | [13 empty] | 450.68 | 119.66 | 26.55