## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-V at Barijpur mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11267 | Retrofitting | 9305 Nos. Functional Household Tap Connection (FHTC) in Zone-V at Barijpur mouza of Mograhat-I block for providing 100% FHTC within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC-9305 Nos.) | AE SWSD-II | JE3 | ORD/000678/2022-2023 | 3457/SWD-I | 14/03/2023 | 01/07/2025 | M/S. S.S. ENTERPRISE | 554.56 | 61.13 | 11.02 | 70
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-V at Barijpur mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11267 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 322/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 57.32 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-V at Barijpur mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11267 | Retrofitting | Construction of 1 (one) no pipe carrying structures for laying of distribution pipeline over Nainpur Deula canal at Node Point 946 - 1205 for the laying of distribution system at Zone-V, Magrahat-I Block within 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME' for Falta-Mathurapur, Dist- South 24 Pgs W/S Division-I, P.H.E. Dte. (SM/11267) |  |  | ORD/000098/2025-2026 | 1773/SWD-I | 02/07/2025 | 16/08/2025 | SRIJON ENTERPRISE | 32.96 | 0 | 0 | 0
Total | [13 empty] | 644.84 | 61.13 | 9.48