## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Construction of 400 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Jhungri Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I | JE-4 | ORD/000307/2022-2023 | 1911/SWD-I | 18/11/2022 | 02/09/2025 | STARCO CONSTRUCTION | 660.5 | 608.02 | 92.05 | 85
2 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR JHUNGRI PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 26, KHATIAN NO. 743, JL. NO. 118, MOUZA - GHUMRI) & 2ND TUBE WELL SITE (DAG NO. 116/1166, KHATIAN NO. 743, JL NO. 118, MOUZA - GHUMRI), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I |  | ORD/000003/2022-2023 | 756/SWD-I | 29/06/2022 | 29/07/2022 | SIMPLEX DRILLING CO. | 28.38 | 26.02 | 91.66 | 100
3 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 1921/SWD-I | 18/11/2022 | 18/11/2022 | Resource Division | 16.4 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Improvement of Outdoor illumination arrangement with allied works at Satberia PH-1 water supply scheme under Bhangar-I Block under SMD, PHE Dte. |  |  | ORD/002572/2023-2024 | 1098/SMSD | 21/08/2023 | 05/09/2023 | DAS ENTERPRISE | 0.88 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone- I of Jhungri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000466/2022-2023 | 277/SMD | 01/02/2023 | 02/05/2023 | DAS ENTERPRISE | 26.01 | 25.31 | 97.34 | 100
6 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Supply & installation of LED board at PH-1&2 of Jhungri w/s scheme under South 24-Pgs Mechanical Division PHE Dte. |  |  | ORD/000867/2023-2024 | 1075/SMSD | 17/08/2023 | 01/09/2023 | M/S. S.R. ENTERPRISE | 0.78 | 0.78 | 100 | 100
7 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Improvement of outdoor illumination arrangement with allied works at Jhungri PH 1 w/s scheme under Bhangar-I under SMD, PHE Dte. |  |  | ORD/001962/2023-2024 | 1O97/SMSD | 21/08/2023 | 05/09/2023 | DAS ENTERPRISE | 0.88 | 0.88 | 100 | 100
8 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Improvement of Outdoor illumination arrangement with allied works at Jhungri PH-2 water supply scheme under Bhangar-I Block under SMD, PHE Dte. |  |  | ORD/002971/2023-2024 | ..1098/SMSD | 21/08/2023 | 05/09/2023 | DAS ENTERPRISE | 0.88 | 0.88 | 100 | 100
9 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 2690/SWD-I | 20/01/2023 | 20/01/2023 | Resource Division | 14.98 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00385/2023-2024 | BP-2023-24-63 | 09/06/2023 | 09/06/2023 | WBSEDCL | 14.73 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Construction of Boundary Wall and others allied works at 2nd TW site of JHUNGRI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11273) |  |  | ORD/000751/2024-2025 | 4673/SWD-I | 18/11/2024 | 02/01/2025 | GANAPATI ENTERPRISE | 11.47 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | JHUNGRI Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11273 | New | Construction of Boundary Wall and others allied works at HW site of JHUNGRI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11273) |  |  | ORD/000562/2024-2025 | 4235/SWD-I | 30/09/2024 | 29/11/2024 | TOJO ENTERPRISE | 36.45 | 0 | 0 | 0
Total | [13 empty] | 812.35 | 661.9 | 81.48