## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1921/SWD-I | 18/11/2022 | 18/11/2022 | Resource Division | 13.92 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Shaksahar Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I | JE-4 | ORD/000227/2022-2023 | 1689/SWD-I | 01/11/2022 | 28/08/2023 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 526.17 | 361.98 | 68.8 | 68
3 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 2689/SWD-I | 20/01/2023 | 20/01/2023 | Resource Division | 15.91 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01109/2023-2024 | BP-2023-24-156 | 24/07/2023 | 24/07/2023 | WBSEDCL | 9.73 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Construction of Boundary wall for proposed OHR Site of SHAKSAHAR Piped Water Suplly Scheme in BHANGAR-I Block in South 24-Pgns West Bengal, under South 24 Paraganas W/S Division-I, P.H.E. Dte. [SM/11275] | AE HQ-I | JE-4 | ORD/000509/2023-2024 | 2247/SWD-I | 13/09/2023 | 13/10/2023 | MS KRISHNA MONDAL | 29.66 | 17.13 | 57.74 | 10
6 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of SHAKSAHAR PWSS within Bhangar-I Block "SHAKSAHAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/11275) |  |  | ORD/000757/2024-2025 | 4678/SWD-I | 18/11/2024 | 17/01/2025 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 77.5 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR SHAKSAHAR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 882, KHATIAN NO. 843, JL. NO. 104, MOUZA - CHAKBHIKA) & 2ND TUBE WELL SITE (DAG NO. 308, KHATIAN NO. 567, JL NO. 119, MOUZA - SHAKSAHAR), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I | JE-3 | ORD/000004/2022-2023 | 757/SWD-I | 29/06/2022 | 29/07/2022 | SIMPLEX DRILLING CO. | 28.39 | 26.63 | 93.8 | 50
8 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Development of low Land and temporary approach road entering 1st Tubewell site for SHAKSAHAR pipe water supply scheme in Bhangar-I block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I, PHE Dte. | AE HQ-I | JE-3 | ORD/000066/2023-2024 | 90/SWD-I | 06/04/2023 | 21/04/2023 | CIVILEX COMBINE | 0.61 | 0.61 | 98.84 | 100
9 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Development of low Land and temporary approach road entering 2nd Tubewell site SHAKSAHAR pipe water supply scheme in Bhangar-I block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I, PHE Dte. | AE HQ-I | JE-3 | ORD/000067/2023-2024 | 91/SWD-I | 06/04/2023 | 21/04/2023 | CIVILEX COMBINE | 0.55 | 0.47 | 85.06 | 100
10 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Additional work for Sinking of 01 (One) no. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achive 66 mtr. housing pipe by Rotary method for SHAKSAHAR PWSS at 2nd Tubewell site of Bhangar-I Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/0010765] | AE HQ-I | JE-3 | ORD/000292/2023-2024 | 1398/SWD-I | 13/07/2023 | 28/07/2023 | SIMPLEX DRILLING COMPANY | 1.57 | 1.57 | 100 | 100
11 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Quotation for new service(power) connection at Shaksahar PH- 2 water supply scheme under bhangar-I block Reference ID- 106550929, Application No- 1007657683 |  |  | BILL/00569/2024-2025 | BP-2024-25-141 | 03/07/2024 | 03/07/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Payment of Enhanced GST Rate vide W/O No.1689/SWD-I dt. 01/11/2022 |  |  | BILL/02030/2023-2024 | BP-2023-24-756 | 13/03/2024 | 13/03/2024 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 19.39 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone- I of Shaksahar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000465/2022-2023 | 276/SMD | 01/02/2023 | 02/04/2025 | DAS ENTERPRISE | 25.77 | 11.98 | 46.49 | 95
14 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Improvement of outdoor Illumination arrangement with allied works at Shakasar PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/11275) | Assistant Engineer | Junior Engineer | ORD/001682/2024-2025 | 1696/SMSD | 24/12/2024 | 08/01/2025 | DAS ENTERPRISE | 0.9 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | SHAKSAHAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgns west Bengal | SM/11275 | New | Supply & installation of LED board at P.H. No-1 & 2 of Shaksahar water supply scheme under South 24-Pgs Mechanical Division PHE Dte.[Bhangar-I][SM/11275] | Assistant Engineer | Junior Engineer | ORD/001617/2024-2025 | 1698/SMSD | 26/12/2024 | 10/01/2025 | SMILE | 0.79 | 0 | 0 | 100
Total | [13 empty] | 755.45 | 420.37 | 55.65