## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Construction of 02 (Two) nos. chlorination room at PURBA GABBERIA (Zone-II) of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD |  | ORD/000158/2022-2023 | 1411/SWD-I | 22/09/2022 | 21/11/2022 | ANANDA MAITY | 11.01 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Purba Gabberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000558/2022-2023 | 572/SMD | 22/02/2023 | 23/05/2023 | DEBJYOTI BASU | 19.37 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Purba Gabberia Zone-II PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010754] | AE BSD |  | ORD/000019/2023-2024 | 42/SWD-I | 06/04/2023 | 21/04/2023 | M/S. S M ENTERPRISE | 4.4 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Preparation and submission of Detailed Project Report of PURBA GABBERIA(II) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000363/2021-2022 | 1930/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100 | 100
5 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 292/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 76.13 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05022/2023-2024 | BP-2023-24-571 | 12/03/2024 | 12/03/2024 | WBSEDCL | 10.24 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at PURBO GABBERIA (Zone-II) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2086) | AE BSD | JE-1 | ORD/000372/2022-2023 | 2316/SWD-I | 19/12/2022 | 06/06/2025 | M/S. S.S. ENTERPRISE | 662.96 | 305.17 | 46.03 | 65
8 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-II) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11276 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PURBA GABBERIA (Zone-II) PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD | JE-1 | ORD/000107/2022-2023 | 1232/SWD-I | 07/09/2022 | 07/10/2022 | M/S. S M ENTERPRISE | 40.13 | 5.44 | 13.55 | 12
Total | [13 empty] | 826.99 | 313.37 | 37.89