## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Construction of 02 (Two) nos. chlorination room at PURBA GABBERIA (Zone-I) of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD |  | ORD/000156/2022-2023 | 1409/SWD-I | 22/09/2022 | 21/11/2022 | NIRMAN | 11.01 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PURBA GABBERIA (Zone-I) PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010747] | AE BSD |  | ORD/000243/2022-2023 | 1686/SWD-I | 01/11/2022 | 01/12/2022 | K P CONSTRUCTION | 42.29 | 35.45 | 83.82 | 90
3 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Preparation and submission of Detailed Project Report of PURBA GABBERIA(I) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000364/2021-2022 | 1929/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.72 | 98.54 | 100
4 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Purba Gabberia Zone-I PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010747] | AE BSD |  | ORD/000018/2023-2024 | 41/SWD-I | 06/04/2023 | 21/04/2023 | K P CONSTRUCTION | 4.41 | 4.23 | 95.97 | 100
5 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 291/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 240.21 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05023/2023-2024 | BP-2023-24-570 | 12/03/2024 | 12/03/2024 | WBSEDCL | 8.55 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at PURBO GABBERIA (Zone-I) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1909) | AE BSD | JE RWS,JE-2 | ORD/000274/2022-2023 | 1808/SWD-I | 09/11/2022 | 21/02/2026 | PASCON | 449.74 | 282.8 | 62.88 | 65
8 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Purba Gabberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000557/2022-2023 | 546/SMD | 21/02/2023 | 01/10/2025 | DEBJYOTI BASU | 19.37 | 0 | 0 | 91
9 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Modified and Allied Electro-Mechanical works at Pump House no-1 of Purba Gabberia Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002275/2024-2025 | 1554/SMSD | 26/11/2024 | 11/12/2024 | DEBJYOTI BASU | 0.94 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Supply and delivery of actuator & Butter fly valve due to some modification held at Pump House no-1 of Purba Gabberia Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002276/2024-2025 | 1553/SMSD | 26/11/2024 | 11/12/2024 | DEBJYOTI BASU | 0.99 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Purba Gabberia (Zone-I) PWSS, Under South 24-Pgns W/S Division-I, Block: Jaynagar-I District South 24-Pgns. | SM/11277 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Purba Gabberia Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11277] | Assistant Engineer | Junior Engineer | ORD/002277/2024-2025 | 17/SMSD | 06/01/2025 | 21/01/2025 | DEBJYOTI BASU | 0.59 | 0 | 0 | 0
Total | [13 empty] | 780.85 | 325.19 | 41.65