## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Construction of 02 (Two) nos. chlorination room at CHAMPAHATI Zone-I of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010744] | AE BSD |  | ORD/000154/2022-2023 | 1407/SWD-I | 22/09/2022 | 21/11/2022 | M/S P. PURKAIT ENTERPRISE. | 10.95 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Champahati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000533/2022-2023 | 460/SMD | 17/02/2023 | 18/05/2023 | K.P CONSTRUCTION | 19.57 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Preparation and submission of Detailed Project Report of CHAMPAHATI(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000451/2021-2022 | 1953/SWD_I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 295/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 17.75 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01987/2023-2024 | BP-2023-24-245 | 11/09/2023 | 11/09/2023 | WBSEDCL | 7.11 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHAMPAHATI Zone-I Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 918) | AE BSD | JE-2 | ORD/000738/2022-2023 | 3591/SWD-I | 23/03/2023 | 17/01/2024 | M/S SUMAN SHIL | 226.66 | 0 | 0 | 30
7 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHAMPAHATI Zone-I PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010744] | AE BSD | JE RWS,JE-2 | ORD/000225/2022-2023 | 1683/SWD-I | 01/11/2022 | 01/12/2022 | K P CONSTRUCTION | 42.29 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Champahati-I PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/010744] | AE BSD | JE RWS,JE-2 | ORD/000783/2022-2023 | 3666/SWD-I | 29/03/2023 | 13/04/2023 | K P CONSTRUCTION | 4.41 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00163/2024-2025 | BP-2024-25-51 | 10/05/2024 | 10/05/2024 | WBSEDCL | 4.46 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Champahati Zone-I PWSS, Under South 24-Pgns W/S Division-I, Block:Baruipur, District South 24-Pgns. | SM/11278 | New | Construction of Platform Development of Land, Pipeline Protection Work and others allied works Ground Water Based CHAMPAHATI ZONE-I PWSS to accommodate FHTC in BARUIPUR Block under South 24 Pgns W/S Divn-I PHE Dte for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District. [SM/11278] | AE BSD | JE-2 | ORD/000791/2024-2025 | 4842/SWD-I | 27/11/2024 | 26/01/2025 | SANKAR MONDAL | 73.66 | 0 | 0 | 30
Total | [13 empty] | 409.61 | 0 | 0