## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 293/SWD-I | 24/04/2023 |  | Resource Division | 38.58 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00010/2023-2024 | BP-2023-24-46 | 18/05/2023 |  | WBSEDCL | 3.13 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Piyali Kolaghat w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Baruipur] |  |  | ORD/000895/2023-2024 | 1O62/SMSD | 10/08/2023 | 25/08/2023 | NUPUR CHANDRA HALDER | 0.87 | 0.86 | 99.6 | 100
4 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Construction of 02 (Two) nos. chlorination room at PIYALI KOLAGHATA (Zone-II) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010734] | AE BSD | JE-2 | ORD/000159/2022-2023 | 1412/SWD-I | 22/09/2022 | 21/11/2022 | M/S. SREEJIT ENTERPRISE | 10.99 | 4.57 | 41.56 | 50
5 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000105/2022-2023 | 1231/SWD-I | 07/09/2022 | 07/10/2022 | BARI ENTERPRISE | 40.12 | 25.3 | 63.06 | 100
6 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/010734] | AE BSD |  | ORD/000456/2023-2024 | 2115/SWD-I | 30/08/2023 | 14/09/2023 | BARI ENTERPRISE | 4.4 | 1.02 | 23.11 | 100
7 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Preparation and submission of Detailed Project Report of PIYALI KOLAGHATA , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000507/2021-2022 | 1906/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 2.76 | 1.38 | 49.99 | 100
8 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-II) (No. of FHTC = 1906) | AE BSD | JE-1 | ORD/000237/2022-2023 | 1712/SWD-I | 02/11/2022 | 02/03/2023 | M/S. S.S. ENTERPRISE | 285.6 | 48.1 | 16.84 | 90
9 | SOUTH 24 PARAGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1& 2, of Piyali Kolaghata water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000532/2022-2023 | 459/SMD | 17/02/2023 | 18/05/2023 | NUPUR CHANDRA HALDER | 21.83 | 15.03 | 68.82 | 80
10 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Construction of Platform for providing FHTC for Ground Water Based PIYALI KOLAGHATA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) |  |  | ORD/000306/2024-2025 | 3219/SWD-I | 18/07/2024 | 16/09/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 35.48 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Construction of boundary wall including development of land and other allied works for Ground water based PIYALI KOLAGHATA(P-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) |  |  | ORD/000312/2024-2025 | 3239/SWD-I | 19/07/2024 | 02/09/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 31.32 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Supply & fixing main switch & Bus Bar at Pump House no-1 of Piyali KOLAGHATA W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11279) | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 490/SMSD | 23/04/2024 | 08/05/2024 | NUPUR CHANDRA HALDER | 0.29 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Piyali KOLAGHATA (Part-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11279) | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 491/SMSD | 23/04/2024 | 08/05/2024 | NUPUR CHANDRA HALDER | 0.89 | 0 | 0 | 100
14 | SOUTH 24 PARAGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at piyali kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-I) (No. of FHTC = 1032) | AE BSD | JE-2 | ORD/000271/2022-2023 | 1798/SWD-I | 09/11/2022 | 07/02/2023 | KARUNAMOYEE ENTERPRISE | 140.23 | 28.5 | 20.33 | 75
Total | [13 empty] | 616.49 | 124.76 | 20.24