## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000105/2022-2023 | 1231/SWD-I | 07/09/2022 | 07/10/2022 | BARI ENTERPRISE | 40.12 | 33.85 | 84.37 | 100
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/010734] | AE BSD |  | ORD/000456/2023-2024 | 2115/SWD-I | 30/08/2023 | 14/09/2023 | BARI ENTERPRISE | 4.4 | 2.03 | 46.21 | 100
3 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Preparation and submission of Detailed Project Report of PIYALI KOLAGHATA , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000507/2021-2022 | 1906/SWD-I | 27/01/2022 | 26/02/2022 | RADIANT | 2.76 | 2.76 | 99.97 | 100
4 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Piyali Kolaghat w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Baruipur] |  |  | ORD/000895/2023-2024 | 1O62/SMSD | 10/08/2023 | 25/08/2023 | NUPUR CHANDRA HALDER | 0.87 | 0.86 | 99.6 | 100
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 293/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 38.58 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00010/2023-2024 | BP-2023-24-46 | 18/05/2023 | 18/05/2023 | WBSEDCL | 3.13 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Construction of 02 (Two) nos. chlorination room at PIYALI KOLAGHATA (Zone-II) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010734] | AE BSD | JE-2 | ORD/000159/2022-2023 | 1412/SWD-I | 22/09/2022 | 21/11/2022 | M/S. SREEJIT ENTERPRISE | 10.99 | 5.93 | 53.94 | 100
8 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Construction of Platform for providing FHTC for Ground Water Based PIYALI KOLAGHATA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) |  |  | ORD/000306/2024-2025 | 3219/SWD-I | 18/07/2024 | 16/09/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 35.48 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Construction of boundary wall including development of land and other allied works for Ground water based PIYALI KOLAGHATA(P-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) |  |  | ORD/000312/2024-2025 | 3239/SWD-I | 19/07/2024 | 02/09/2024 | M/S. S.S. ENTERPRISE (NODAKHALI) | 31.32 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1& 2, of Piyali Kolaghata water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000532/2022-2023 | 459/SMD | 17/02/2023 | 18/05/2023 | NUPUR CHANDRA HALDER | 21.83 | 20.76 | 95.07 | 100
11 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Piyali KOLAGHATA (Part-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11279) | Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 491/SMSD | 23/04/2024 | 08/05/2024 | NUPUR CHANDRA HALDER | 0.89 | 0.88 | 99.21 | 100
12 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-II) (No. of FHTC = 1906) | AE BSD | JE-1 | ORD/000237/2022-2023 | 1712/SWD-I | 02/11/2022 | 30/07/2025 | M/S. S.S. ENTERPRISE | 285.6 | 96.2 | 33.68 | 92
13 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at piyali kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-I) (No. of FHTC = 1032) | AE BSD | JE-2 | ORD/000271/2022-2023 | 1798/SWD-I | 09/11/2022 | 26/07/2025 | KARUNAMOYEE ENTERPRISE | 140.23 | 57.01 | 40.65 | 75
14 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Baruipur Sub-Division under South 24-Pgns. W/S Division-I, PHE Dte. [WB04J1932] [SM/11279] [w.e.f. 01/01/2025 to 30/06/2025] | AE BSD | JE RWS, Bhangar-II Block,JE-2 | ORD/001109/2024-2025 | 5303/SWD-I | 27/12/2024 | 26/06/2025 | SUBRAT KUMAR SETHY | 0.86 | 2.08 | 241.72 | 33
15 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for PIYALI KOLAGHATA (PART-I) Piped Water Supply Scheme of BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/11279] |  |  | ORD/001154/2024-2025 | 372/SWD-I | 04/02/2025 | 06/03/2025 | M/S MAA TARA ENTERPRISE | 15.65 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Baruipur Sub-Division under South 24-Pgns. W/S Division-I, PHE Dte. [WB04J1932] [SM/11279] [w.e.f. 01/07/2025 to 31/12/2025] | AE BSD | JE-2 | ORD/000121/2025-2026 | 1730/SWD-I | 26/06/2025 | 27/12/2025 | SUBRAT KUMAR SETHY | 0.87 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Supply & fixing main switch & Bus Bar at Pump House no-1 of Piyali KOLAGHATA W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11279) | Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 490/SMSD | 23/04/2024 | 08/05/2024 | NUPUR CHANDRA HALDER | 0.29 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata Baruipur Block within South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. | SM/11279 | New | Charges for new service connection pump house no-I of Piyali Kolaghata (Part-II) water supply scheme (Baruipur Block) |  |  | BILL/02787/2024-2025 | BP-2024-25-576 | 20/03/2025 | 20/03/2025 | WBSEDCL | 7.49 | 0 | 0 | 0
Total | [13 empty] | 641.37 | 222.35 | 34.67