## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GOBINDAPUR PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010741] | AE BSD | JE-1 | ORD/000242/2022-2023 | 1685/SWD-I | 01/11/2022 | 27/10/2023 | SIMPLEX DRILLING COMPANY | 42.98 | 37.32 | 86.83 | 100
2 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Preparation and submission of Detailed Project Report of GOBINDAPUR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000448/2021-2022 | 1962/SWD-I | 21/01/2022 | 20/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100 | 100
3 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Construction of 02 (Two) nos. chlorination room at GOBINDAPUR of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD | JE-1 | ORD/000157/2022-2023 | 1410/SWD-I | 22/09/2022 | 06/09/2025 | J H K ENTERPRISE | 11.01 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at GOBINDAPUR Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1510) | AE BSD | JE-1 | ORD/000351/2023-2024 | 1737/SWD-I | 10/08/2023 | 26/01/2026 | TAAS ENTERPRISE | 511.22 | 387.99 | 75.89 | 85
5 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000556/2022-2023 | 545/SMD | 21/02/2023 | 01/06/2025 | DEBJYOTI BASU | 19.37 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Jaynagar-I | South 24 Pgs W/S Division I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 292/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 45.97 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04088/2023-2024 | BP-2023-24-423 | 16/12/2023 | 16/12/2023 | WBSEDCL | 15.69 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gobindapur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11280] | Assistant Engineer | Junior Engineer | ORD/002274/2024-2025 | 1520/SMSD | 18/11/2024 | 03/12/2024 | DEBJYOTI BASU | 0.59 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Jaynagar-I | S24 Pgns Mechanical | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Gobindapur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11280] | Assistant Engineer | Junior Engineer | ORD/002273/2024-2025 | 18/SMSD | 06/01/2025 | 21/01/2025 | DEBJYOTI BASU | 0.59 | 0 | 0 | 0
Total | [13 empty] | 650.18 | 428.06 | 65.84