## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHAKRABORTY ABAD PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009670] | AE BSD |  | ORD/000241/2022-2023 | 1684/SWD-I | 01/11/2022 | 01/12/2022 | SIMPLEX DRILLING COMPANY | 21.48 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chakraborty Abad PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD |  | ORD/000632/2022-2023 | 3261/SWD-I | 02/03/2023 | 17/03/2023 | SIMPLEX DRILLING COMPANY | 2.24 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Chakraborty Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000526/2022-2023 | 439/SMD | 17/02/2023 | 18/05/2023 | A.S ENGINEERING | 13.01 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1100) | AE BSD | JE-1 | ORD/000185/2022-2023 | 1488/SWD-I | 28/09/2022 | 26/01/2023 | TANMOY ROY CHOWDHURY | 197.72 | 0 | 0 | 77
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Construction of chlorination room at CHAKRABORTY ABAD of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009670] | AE BSD |  | ORD/000290/2022-2023 | 1785/SWD-I | 07/11/2022 | 06/01/2023 | SANJAY ENTERPRISE | 5.8 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 6.78 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Material Requisition To Resource Division |  |  | RTOR000277/2023-2024 | 2426/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 1.73 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Balance miscellaneous work for Ground Water Based Water Supply Scheme at CHAKRABORTY ABAD (Kalabaru, JL-114) Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns District. (SM/11296) | AE BSD | JE-1 | ORD/000913/2023-2024 | 1203/SWD-I | 11/03/2024 | 20/01/2025 | UNI DEVELOPERS AND CONTRACTORS | 23.98 | 0 | 0 | 40
9 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114), Baruipur Block under South 24 Parganas dist | SM/11296 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04654/2023-2024 | BP-2023-24-493 | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.79 | 0 | 0 | 0
Total | [13 empty] | 276.52 | 0 | 0