## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | SM/11297 | New | Preparation and submission of Detailed Project Report of MALLIKPUR, PART-I Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000222/2021-2022 | 1958/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.62 | 2.51 | 95.95 | 100
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | SM/11297 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Mallickpur (Mallickpur C.T, J.L- 10) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (PART-I) (No. of FHTC = 813) | AE BSD |  | ORD/000269/2022-2023 | 1799/SWD-I | 09/11/2022 | 07/02/2023 | DIPALI CONSTRUCTION | 102.68 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | SM/11297 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Mallikput water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000531/2022-2023 | 458/SMD | 17/02/2023 | 18/05/2023 | BARISAL TRADING CO. | 13.01 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | SM/11297 | New | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 296/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 5.99 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | SM/11297 | New | Sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tubewell by Rotary method for MALLICKPUR (Part-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte., within South 24 Parganas District under JJM. [AAFS - GO22223004569PH] [Project ID- PH222355766S000] | AE BSD | JE RWS | ORD/000069/2022-2023 | 1114/SWD-I | 23/08/2022 | 05/12/2025 | PADMA ENGINEERING CO. | 20.08 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Mallikput (Mallikpur CT,J.L-10), Baruipur Block under South 24 Parganas dist.(PART-I) | SM/11297 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Mallikpur (I) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/009674] | AE BSD | JE RWS | ORD/000800/2022-2023 | 3672/SWD-I | 29/03/2023 | 13/11/2025 | PADMA ENGINEERING CO. | 2.2 | 0 | 0 | 100
Total | [13 empty] | 146.59 | 2.51 | 1.71