## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PIYALI KOLAGHATA (Part-I) PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009673] | AE BSD |  | ORD/000101/2022-2023 | 1228/SWD-I | 07/09/2022 | 07/10/2022 | SAIKAT ENTERPRISE | 19.98 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Construction of chlorination room at PIYALI KOLAGHATA (Zone-I) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009673] | AE BSD |  | ORD/000155/2022-2023 | 1413/SWD-I | 22/09/2022 | 21/11/2022 | SHUBHA UDYOG | 5.5 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PiyaliKolaghata-I PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD |  | ORD/000729/2022-2023 | 3572/SWD-I | 22/03/2023 | 06/04/2023 | SAIKAT ENTERPRISE | 2.2 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Piyali Kolaghata ( Solghoalia CT) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000530/2022-2023 | 443/SMD | 17/02/2023 | 18/05/2023 | RSA ENTERPRISE | 13.01 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 293/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 8.71 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00161/2024-2025 | BP-2024-25-53 | 10/05/2024 | 10/05/2024 | WBSEDCL | 5.31 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-II) (No. of FHTC = 1906) | AE BSD | JE-1 | ORD/000237/2022-2023 | 1712/SWD-I | 02/11/2022 | 30/07/2025 | M/S. S.S. ENTERPRISE | 285.6 | 140.4 | 49.16 | 92
8 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia CT, J.L-25), Baruipur block under South 24 Parganas Dist. (Part-I) | SM/11298 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at piyali kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-I) (No. of FHTC = 1032) | AE BSD | JE-2 | ORD/000271/2022-2023 | 1798/SWD-I | 09/11/2022 | 26/07/2025 | KARUNAMOYEE ENTERPRISE | 140.23 | 44.53 | 31.75 | 75
Total | [13 empty] | 480.55 | 184.93 | 38.48