## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009671] | AE BSD |  | ORD/000104/2022-2023 | 1230/SWD-I | 07/09/2022 | 07/10/2022 | DIPALI CONSTRUCTION | 20.07 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Harendrapally water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000528/2022-2023 | 441/SMD | 17/02/2023 | 18/05/2023 | K.S.P ENTERPRISE | 13 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD |  | ORD/000784/2022-2023 | 3674/SWD-I | 29/03/2023 | 13/04/2023 | DIPALI CONSTRUCTION | 2.2 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 7.02 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of BARUIPUR Block for under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/009671] | AE BSD | JE-2 | ORD/000722/2023-2024 | 323/SWD-I | 11/01/2024 | 10/02/2024 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 20.07 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD | JE RWS,JE-1,JE-2 | ORD/000723/2023-2024 | 324/SWD-I | 11/01/2024 | 26/01/2024 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 2.2 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Baruipur | Alipore Division | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Road restoration of L030-Belegachhi Buks Stand on T01 to Sardarpara(WB/02/416) |  |  | BILL/01729/2024-2025 | BP-2024-25-793 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.35 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Charges for new service connection at Harendrapally pump house-I |  |  | BILL/00218/2024-2025 | BP-2024-25-72 | 16/05/2024 | 16/05/2024 | WBSEDCL | 13.08 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Construction of chlorination room at HARENDRAPALLY of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009671] | AE BSD | JE-2 | ORD/000293/2022-2023 | 1787\SWD-I | 07/11/2022 | 06/01/2023 | SANJAY ENTERPRISE | 5.8 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based piped water supply scheme at Harendrapally (Atniramish,J.L-141), Baruipur Block under South 24 Parganas dist | SM/11299 | New | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Harendrapally ( Atniramish, J.L-141) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 910) | AE BSD | JE-2 | ORD/000280/2022-2023 | 1842/SWD-I | 11/11/2022 | 29/04/2025 | A. G. ENTERPRISE | 121.8 | 0 | 0 | 75
Total | [13 empty] | 206.59 | 0 | 0