## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Rania & Kuchigadi village of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I |  | ORD/000109/2022-2023 | 1239/SWD-I | 08/09/2022 | 08/10/2022 | M/S. S.S. ENTERPRISE | 20.09 | 18.73 | 93.25 | 100
2 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Laying of Upvc pipeline for retrofitting of distribution system of KUCHIGADI (PART) Village & RANIA GOBINDAPUR (PART) under SWD - I, P.H.E. Dte District South 24 Parganas. (No. of FHTC = 632) | AE SWSD-I |  | ORD/000240/2022-2023 | 1727/SWD-I | 03/11/2022 | 01/02/2023 | FIDERE MARINE SERVICES PVT LTD. | 100.42 | 100.25 | 99.83 | 80
3 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I |  | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 30/01/2023 | M/S. SREEJIT ENTERPRISE | 19 | 11.3 | 59.5 | 98
4 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Laying of Upvc pipeline for retrofitting of distribution system of Part of Chak Kashipur and Chak Alampur Village under SWD - I, P.H.E. Dte District South 24 Parganas. [SM/11487] | AE SWSD-I |  | ORD/000257/2022-2023 | 1698/SWD-I | 01/11/2022 | 30/01/2023 | TIYASHA ENTERPRISE | 65.45 | 45.12 | 68.94 | 100
5 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Interconnection of pipeline from proposed Tubewell to Distribution Main for Chak Kashipur (Part) & Chak Alampur(Part) of Budge Budge II Block under South 24 Pgs W/S Division-I, PHE Dte. [SM/11487] | AE SWSD-I |  | ORD/000259/2022-2023 | 1700/SWD-I | 01/11/2022 | 16/12/2022 | S.R. CONSTRUCTION | 3.94 | 3.87 | 98.37 | 0
6 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Burul Village (Part) of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I |  | ORD/000108/2022-2023 | 1238/SWD-I | 08/09/2022 | 08/10/2022 | PADMA ENGINEERING CO. | 20.09 | 18.8 | 93.6 | 100
7 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Chakmanik village (Part) of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I |  | ORD/000110/2022-2023 | 1240/SWD-I | 08/09/2022 | 08/10/2022 | VISHAL CONSTRUCTION CO. | 20.08 | 18.5 | 92.11 | 100
8 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Preparation and submission of Route Survey and pipeline network design of "SEKHPARA & BURUL Ground Water Based Piped Water Supply Scheme" in BUDGE BUDGE-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-I |  | ORD/000537/2022-2023 | 471/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.01 | 2.01 | 100 | 100
9 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Preparation and submission of Route Survey and pipeline network design of "RANIA KUCHIGADI & CHAKMANIK Ground Water Based Piped Water Supply Scheme" in BUDGE BUDGE-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-I |  | ORD/000535/2022-2023 | 472/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 1.9 | 1.85 | 97.6 | 100
10 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chakmanik village (Part) of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. | AE SWSD-I |  | ORD/000289/2022-2023 | 1782/SWD-I | 07/11/2022 | 06/01/2023 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 8.54 | 8.34 | 97.67 | 100
11 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Laying of Upvc pipeline for retrofitting of distribution system of Burul (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I | JE-2 | ORD/000238/2022-2023 | 1713/SWD-I | 02/11/2022 | 02/03/2023 | M/S. S.S. ENTERPRISE | 165.97 | 153.9 | 92.73 | 90
12 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Repairing of Pump House and construction of toilet at tubewell site of Chak Kashipur (Part) & Chak Alampur (Part) of Budge Budge-II under South 24-Pgns W/S Division-I, PHE Dte. [SM/11487] | AE SWSD-I |  | ORD/000258/2022-2023 | 1699/SWD-I | 01/11/2022 | 31/12/2022 | ROYAL CONSTRUCTION | 4.54 | 4.45 | 98.12 | 100
13 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Supplying, Fabrication, Erection and Commissioning of Pressure Type Iron Elimination Plant (35 Cum capacity) including other allied works at Satgachia village of Budge Budge-II Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. [TSM/010530] | AE SWSD-I |  | ORD/000383/2022-2023 | 2362/SWD-I | 22/12/2022 | 21/05/2023 | RAMASISH ENTERPRISE | 16.78 | 16.71 | 99.63 | 100
14 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Rania & Kuchigadi village of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/010530] | AE SWSD-I |  | ORD/000112/2022-2023 | 1242/SWD-I | 08/09/2022 | 07/11/2022 | M/S. DAS ENTERPRISE | 8.03 | 7.77 | 96.79 | 100
15 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.5 (Chakmanik) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000274/2022-2023 | 3918/SMD | 30/12/2022 | 30/03/2023 | WIZARDTECH SOLUTION | 11.11 | 10.96 | 98.66 | 100
16 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Laying of pipe line for interconnection from proposed Tubewell to Distribution Main for Burul Village (Part) to Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000054/2022-2023 | 1014/SWD-I | 02/08/2022 | 01/10/2022 | AHANA ENTERPRISE | 3.81 | 3.76 | 98.69 | 100
17 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Construction of Blower room (Size 3.60m X 3.00m) at Burul Village (Part) of Budge Budge-II block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000057/2022-2023 | 1015/SWD-I | 02/08/2022 | 01/10/2022 | AHANA ENTERPRISE | 3.07 | 2.99 | 97.53 | 100
18 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Construction of Blower room (Size 3.60m X 3.00m) at Chakmanik Village (Part) Village of Budge Budge-II block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000059/2022-2023 | 1019/SWD-I | 02/08/2022 | 01/10/2022 | MS POUSALI ENTERPRISE | 3.06 | 2.99 | 97.76 | 100
19 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Laying of pipe line for interconnection from proposed Tubewell to Distribution Main for Rania & Kuchigadi Village to Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000055/2022-2023 | 1016/SWD-I | 02/08/2022 | 01/10/2022 | HASIBA ENTERPRISE | 3.81 | 3.76 | 98.69 | 100
20 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Sinking of 01 no. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Chak Kashipur (Part) & Chak Alampur (Part) of Budge Budge-II block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010530] | AE SWSD-I |  | ORD/000329/2022-2023 | 2047/SWD-I | 30/11/2022 | 30/12/2022 | BARI ENTERPRISE | 21.09 | 18.85 | 89.39 | 100
21 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Laying of pipeline for retrofitting of distribution system of Chakmanik Village under South 24-Parganas Water Supply Division-I, P.H.E. Dte. District South 24 Parganas. [TSM/010530] | AE SWSD-I | JE-2 | ORD/000163/2022-2023 | 1408/SWD-I | 22/09/2022 | 21/12/2022 | M/S. S.S. ENTERPRISE | 77.23 | 72.48 | 93.85 | 80
22 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Burul Village (Part) of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/010530] | AE SWSD-I |  | ORD/000111/2022-2023 | 1241/SWD-I | 08/09/2022 | 07/11/2022 | SANJAY MIDDEY | 5.41 | 5.17 | 95.56 | 100
23 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 1573 | 16/10/2022 | 16/10/2022 | Resource Division | 16.2 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/12/2023 to 31/05/2024] [Vehicle No:- WB-19L-3415] | AE HQ-II | JE-2 | ORD/000664/2023-2024 | 2997/SWD-I | 29/11/2023 | 30/05/2024 | AVIK HALDER | 0.89 | 1.57 | 177.44 | 30
25 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Road crossing of pipeline for interconnection of LDS under Zone-1, 3 & 5 PWSS at 02 locations under Budge Budge-II Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (TSM/10530) | AE SWSD-I |  | ORD/000745/2022-2023 | 3596/SWD-I | 23/03/2023 | 07/04/2023 | S. ROY AND ASSOCIATES | 7.88 | 7.85 | 99.67 | 0
26 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Balance Upvc Pipeline laying at Burul W/S Scheme for Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs.(TSM/010530) | AE SWSD-I |  | ORD/000045/2023-2024 | 184/SWD-I | 18/04/2023 | 18/05/2023 | ARKADEEP ENTERPRISE | 19.78 | 19.78 | 100 | 100
27 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.1 (Burul) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000270/2022-2023 | 219/SMD | 20/01/2023 | 20/04/2023 | SARKAR ELECTRICAL | 11.11 | 10.92 | 98.3 | 100
28 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.1 (Rania) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000269/2022-2023 | 218/SMD | 20/01/2023 | 20/04/2023 | COOLING CARE CENTER | 11.11 | 11.02 | 99.18 | 100
29 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method at ChakAlampur Village for Zone- 1,3&5 PWSS of Budge Budge-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010530] | AE SWSD-I |  | ORD/000695/2022-2023 | 3498/SWD-I | 16/03/2023 | 31/03/2023 | BARI ENTERPRISE | 2.2 | 2.2 | 100 | 100
30 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.3 (Kashipur Alampur) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000272/2022-2023 | 244/SMD | 27/01/2023 | 27/04/2023 | S.R. CONCERN | 10.97 | 10.77 | 98.13 | 100
31 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Payment for electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01791/2022-2023 | BP-2022-23-459 | 23/03/2023 | 23/03/2023 | WBSEDCL | 0.76 | 0 | 0 | 0
32 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02559/2023-2024 | BP-2023-24-266 | 18/09/2023 | 18/09/2023 | WBSEDCL | 0.44 | 0 | 0 | 0
33 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00394/2023-2024 | BP-2023-24-61 | 09/06/2023 | 09/06/2023 | WBSEDCL | 1.96 | 0 | 0 | 0
34 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Bill for Security Deposit for New Service Connection |  |  | BILL/01262/2022-2023 | BP-2022-23-439 | 10/03/2023 | 10/03/2023 | WBSEDCL | 3.05 | 0 | 0 | 0
35 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02639/2023-2024 | BP-2023-24-278 | 03/10/2023 | 03/10/2023 | WBSEDCL | 0.57 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/00372/2023-2024 | BP-2023-24-27 | 17/05/2023 | 17/05/2023 | WBSEDCL | 1.98 | 0 | 0 | 0
37 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2024 to 30/11/2024] [Vehicle No:- WB-19L-3415] | AE HQ-I | JE-2 | ORD/000288/2024-2025 | 2481/SWD-I | 28/05/2024 | 27/11/2024 | AVIK HALDER | 0.89 | 2.38 | 268.54 | 0
38 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/12/2024 to 31/05/2025] [Vehicle No:- WB-19L-3415] | AE HQ-I | JE-2 | ORD/000888/2024-2025 | 4875/SWD-I | 29/11/2024 | 30/05/2025 | AVIK HALDER | 0.88 | 1.17 | 132.79 | 0
39 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Construction of 3 (Three) nos. boundary walls for Providing FHTC with allied works for Zone-1, 3 & 5 of Budge Budge-II Block under South 24- parganas W/S Division-I, P.H.E. Dte. of South 24-Pargans District (SM/11487) | AE SWSD-I | JE-2 | ORD/000363/2024-2025 | 3505/SWD-I | 07/08/2024 | 21/09/2024 | MS KRISHNA MONDAL | 44.65 | 16.67 | 37.32 | 50
40 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Providing pipe supporting structures at Burul Water Supply Scheme and other allied works under Providing FHTC with allied works for Zone 1, Zone-3 & Zone-5 of Budge Budge-II under South 24-pgns. Water Supply Division.-I, PHE Dte. Dist- South 24-Pgns. (SM/11487) |  |  | ORD/000721/2023-2024 | 363/SWD-I | 16/01/2024 | 16/03/2024 | SOURIK ENTERPRISE | 4.33 | 4.16 | 96.05 | 100
41 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Miscellaneous works in the interest of maintaining proper operational condition at OHR Zone No. 1 (Burul) Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-II) (SM/11487) | Assistant Engineer -II | Junior Engineer | ORD/002103/2023-2024 | 143-AE-II-SMD | 06/02/2024 | 21/02/2024 | M/S. GLOBAL POWER CONCERN | 0.75 | 0.49 | 65.8 | 100
42 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Supply and fitting fixing additional luminaries, LED glow sign board etc at PH No-1 under OHR Zone No- 5 (Chakmanik) Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-II) (SM/11487) | Assistant Engineer -II | Junior Engineer | ORD/002101/2023-2024 | 144-AE-II-SMD | 06/02/2024 | 21/02/2024 | KUNAL ENTERPRISE | 0.75 | 0.75 | 100 | 100
43 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Supply and delivery of Chair, table etc including miscellaneous electrical works at OHR Zone No. 1 (Rania) Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-II) (SM/11487) | Assistant Engineer -II | Junior Engineer | ORD/002238/2023-2024 | 149-AE-II-SMD | 07/02/2024 | 22/02/2024 | SUDIP PRADHAN | 0.75 | 0.75 | 100 | 100
44 | SOUTH 24 PARGANAS | Budge Budge-II | S24 Pgns Mechanical | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Miscellaneous upliftment works in connection with the external illumination arrangement including other allied works at OHR Zone No. 3 (Kashipur Alampur) Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Budge Budge - II)(SM/11487) | Assistant Engineer -II | Junior Engineer | ORD/002104/2023-2024 | 142-AE-II-SMD | 06/02/2024 | 21/02/2024 | SOHINI ENTERPRISE | 0.75 | 0.75 | 100 | 100
45 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Providing pipe supporting structures and other allied works ar different locations for Providing FHTC with allied works for zone-1, 3 & 5 of Budge Budge -II Block under South 24 Parganas W/S Division-I, P.H.E. Dte. of South 24-Pgns District. (SM/11487) | AE SWSD-I | JE-2 | ORD/000383/2024-2025 | 3574/SWD-I | 12/08/2024 | 26/09/2024 | AHANA ENTERPRISE | 9.3 | 0 | 0 | 100
46 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2025 to 30/11/2025] [Vehicle No:- WB-19L-3415] | AE HQ-I | JE-2 | ORD/000059/2025-2026 | 1368/SWD-I | 22/05/2025 | 21/11/2025 | AVIK HALDER | 0.89 | 0 | 0 | 0
47 | SOUTH 24 PARGANAS | Budge Budge-II | South 24 Pgs W/S Division I | Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs. | SM/11487 | New | Construction of 1 (One) no. boundary wall at Burul for Providing FHTC with allied works for Zone-1, 3 & 5 of Budge Budge-II Block under South 24 Parganas W/S Division-I, P.H.E. Dte. of South 24-Pargans District (SM/11487) |  |  | ORD/000017/2025-2026 | 969/SWD-I | 09/04/2025 | 08/06/2025 | MS POUSALI ENTERPRISE | 12.01 | 0 | 0 | 0
Total | [13 empty] | 750.28 | 623.83 | 83.15