## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1984/SWD-I | 25/11/2022 | 25/11/2022 | Resource Division | 45.95 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Investigation of Soil for the proposed Over Head Reservoir (Capacity - 1200 m3) site inside Zone no.- II (Mouza-Goney Gangadharpur, JL No.- 25, Plot No.- 694) of Asuti-I/Asuti-II and Chata GP W/S Scheme within Thakurpukur Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I |  | ORD/000461/2021-2022 | 1222/SWD-I | 12/11/2021 | 12/12/2021 | G TECH INDIA | 0.54 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Laying Rising Main from proposed Tubewell to existing OHR for Zone II with interconnection and bypass arrangement of Asuti W/S Scheme within Thakurpukur-Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000260/2022-2023 | 1701/SWD-I | 01/11/2022 | 31/12/2022 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 58.23 | 0 | 0 | 65
4 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Construction of Boundary wall with allied works for Balance Pump House Sites under Chatta Water Supply Scheme of Thakurpukur Mahestala Block, under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/11488) |  |  | ORD/000774/2023-2024 | 801/SWD-I | 16/02/2024 | 16/04/2024 | RIDIP ENTERPRISE | 26.52 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Laying of 63mm & 75 mm dia balance pipeline for piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 Pgns. W/S Division-I, PHE Dte. (TSM/010374) | AE SWSD-I |  | ORD/000661/2022-2023 | 3377/SWD-I | 10/03/2023 | 09/05/2023 | M/S. S.S. ENTERPRISE | 36.25 | 0 | 0 | 95
6 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Land Development of Rameswarpur Pump House 2nd Site with construction of approach road to facilitate the boring of Tubewell under Pipe Water Supply of Chatta W/S Scheme under South 24 Pgns W/S Division-I , PHE Dte. (SM/11488) | AE SWSD-I | JE-2 | ORD/000775/2023-2024 | 803/SWD-I | 16/02/2024 | 23/02/2024 | MS POUSALI ENTERPRISE | 6.86 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Providing FHTC for Zone I (Part) and adjoining areas under Thakurpukur Maheshtala Block, PHE Dte. under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I | JE-2 | ORD/000007/2022-2023 | 821/SWD-I | 08/07/2022 | 02/07/2025 | M/S. S.S. ENTERPRISE | 316.71 | 0 | 0 | 80
8 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Construction of Over Head Reservoir of capacity 1250 cum at ZONE - II of Asuti-I/II & Chata water supply scheme under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I | JE-1 | ORD/000152/2022-2023 | 1392/SWD-I | 21/09/2022 | 31/05/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 309.69 | 0 | 0 | 90
9 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Supplying, Fabrication, Erection, Commissioning, Trail Run (3 Months) and 1 (one) year Operation & Maintenance of 2 Nos. Pressure Type Iron Elimination Plant (310 Cum capacity) for Zone-I of Chata GP PWSS and (300 Cum capacity) for Zone-II of Asuti-I & Asuti-II GP PWSS in Thakurpukur-Maheshtala Block including other allied works under South 24 Pgs W/S Divn-I, P.H.E. Dte. | AE SWSD-I | JE-1,JE-2 | ORD/000121/2023-2024 | 536/SWD-I | 11/05/2023 | 30/04/2025 | WATREAT ENGINEERS | 184.41 | 0 | 0 | 50
Total | [13 empty] | 985.16 | 0 | 0