## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1984/SWD-I | 25/11/2022 | 25/11/2022 | Resource Division | 45.95 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Investigation of Soil for the proposed Over Head Reservoir (Capacity - 1200 m3) site inside Zone no.- II (Mouza-Goney Gangadharpur, JL No.- 25, Plot No.- 694) of Asuti-I/Asuti-II and Chata GP W/S Scheme within Thakurpukur Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I |  | ORD/000461/2021-2022 | 1222/SWD-I | 12/11/2021 | 12/12/2021 | G TECH INDIA | 0.54 | 0.54 | 100 | 100
3 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Laying Rising Main from proposed Tubewell to existing OHR for Zone II with interconnection and bypass arrangement of Asuti W/S Scheme within Thakurpukur-Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000260/2022-2023 | 1701/SWD-I | 01/11/2022 | 31/12/2022 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 58.23 | 17.5 | 30.06 | 65
4 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Construction of Boundary wall with allied works for Balance Pump House Sites under Chatta Water Supply Scheme of Thakurpukur Mahestala Block, under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/11488) |  |  | ORD/000774/2023-2024 | 801/SWD-I | 16/02/2024 | 16/04/2024 | RIDIP ENTERPRISE | 26.52 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Laying of 63mm & 75 mm dia balance pipeline for piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 Pgns. W/S Division-I, PHE Dte. (TSM/010374) | AE SWSD-I |  | ORD/000661/2022-2023 | 3377/SWD-I | 10/03/2023 | 09/05/2023 | M/S. S.S. ENTERPRISE | 36.25 | 14.77 | 40.74 | 95
6 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Land Development of Rameswarpur Pump House 2nd Site with construction of approach road to facilitate the boring of Tubewell under Pipe Water Supply of Chatta W/S Scheme under South 24 Pgns W/S Division-I , PHE Dte. (SM/11488) | AE SWSD-I | JE-2 | ORD/000775/2023-2024 | 803/SWD-I | 16/02/2024 | 23/02/2024 | MS POUSALI ENTERPRISE | 6.86 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Providing FHTC for Zone I (Part) and adjoining areas under Thakurpukur Maheshtala Block, PHE Dte. under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I | JE-2 | ORD/000007/2022-2023 | 821/SWD-I | 08/07/2022 | 02/07/2025 | M/S. S.S. ENTERPRISE | 316.71 | 75.97 | 23.99 | 80
8 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Construction of Over Head Reservoir of capacity 1250 cum at ZONE - II of Asuti-I/II & Chata water supply scheme under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I | JE-1 | ORD/000152/2022-2023 | 1392/SWD-I | 21/09/2022 | 31/05/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 309.69 | 177.97 | 57.47 | 90
9 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Supplying, Fabrication, Erection, Commissioning, Trail Run (3 Months) and 1 (one) year Operation & Maintenance of 2 Nos. Pressure Type Iron Elimination Plant (310 Cum capacity) for Zone-I of Chata GP PWSS and (300 Cum capacity) for Zone-II of Asuti-I & Asuti-II GP PWSS in Thakurpukur-Maheshtala Block including other allied works under South 24 Pgs W/S Divn-I, P.H.E. Dte. | AE SWSD-I | JE-1,JE-2 | ORD/000121/2023-2024 | 536/SWD-I | 11/05/2023 | 30/04/2025 | WATREAT ENGINEERS | 184.41 | 0 | 0 | 50
10 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Balance interconnection Laying of Rising Main from proposed Tubewell to existing OHR for zone I with interconnection and bypass arrangement for Piped Water Supply Scheme including FHTC for Chatta GP in Thakurpukur-Maheshtala Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/11488) | AE SWSD-I | JE-2 | ORD/000780/2023-2024 | 808/SWD-I | 16/02/2024 | 30/08/2025 | M/S. S.S. ENTERPRISE (NODAKHALI) | 11.24 | 0 | 0 | 50
11 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Road Restoration damaged due to laying of pipeline at CHATTA Gp and adjoining areas under command area of piped water supply scheme including FHTC for CHATTA GP in Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11488) | AE SWSD-I | JE-2 | ORD/000768/2024-2025 | 4689/SWD-I | 18/11/2024 | 31/08/2025 | M/S. S.S. ENTERPRISE (NODAKHALI) | 33.8 | 0 | 0 | 80
12 | SOUTH 24 PARGANAS | Thakurpukur Mahestola | South 24 Pgs W/S Division I | Piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 pgs. W/S Division-I, PHE Dte. | SM/11488 | New | Providing pipe supporting and other allied works at Chatta Kalikapur and Rameswarpur under Chatta W/S Scheme of South 24 Pgns W/S Division-I, PHE Dte. (SM/11488) | AE SWSD-I | JE-2 | ORD/000777/2023-2024 | 805/SWD-I | 16/02/2024 | 31/01/2025 | M/S. S.S. ENTERPRISE (NODAKHALI) | 27.24 | 0 | 0 | 50
Total | [13 empty] | 1057.44 | 286.74 | 27.12