## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for ALIPOREPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II | JE2 | ORD/000031/2022-2023 | 915/SWD-I | 19/07/2022 | 18/08/2022 | SIMPLEX DRILLING CO. | 14.18 | 13.06 | 92.09 | 100
2 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Preparation and submission of Detailed Project Report of "ALIPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000400/2022-2023 | 458/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.51 | 2.5 | 99.79 | 100
3 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Material Requisition To Resource Division |  |  | RTOR000116/2022-2023 | 3249/SWD-I | 01/03/2023 |  | Resource Division | 32.09 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ALIPORE PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011230] | AE SWSD-II | JE2 | ORD/000507/2022-2023 | 2905/SWD-I | 14/02/2023 | 01/03/2023 | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 100 | 100
5 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Development of low land and temporary aproach road for entering Tubewell site for proposed ALIPORE Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011230] | AE SWSD-II | JE2 | ORD/000811/2022-2023 | 3703/SWD-I | 30/03/2023 | 14/04/2023 | SIMPLEX DRILLING COMPANY | 0.88 | 0.75 | 84.78 | 100
6 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Alipore water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000468/2022-2023 | 279/SMD | 01/02/2023 | 02/05/2023 | NITESH MANAGEMENT | 26.52 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Land Development at 1st Tubewell site under Alipore PWSS to accommodate FHTC in Bishnupur-I Block under South 24 pgs W/S Division-I, P.H.E Dte. [TSM/011230] | AE SWSD-II |  | ORD/000245/2023-2024 | 1487/SWD-I | 19/07/2023 | 03/08/2023 | MAA LAXMI ENTERPRISE | 2.97 | 2.97 | 99.92 | 100
8 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 1583/SWD-I | 17/10/2022 |  | Resource Division | 6.39 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of ALIPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11493) (3rd Call) | AE SWSD-II |  | ORD/000251/2023-2024 | 1498/SWD-I | 20/07/2023 | 18/09/2023 | RAMASISH ENTERPRISE | 5.91 | 0 | 0 | 1
10 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for ALIPORE PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011230] | AE SWSD-II | JE2 | ORD/000597/2022-2023 | 3124/SWD-I | 24/02/2023 | 26/03/2023 | CIVIL CONSULTANT | 15.88 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed ALIPORE PIPE WATER SUPPLY SCHEME Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 1038] | AE SWSD-II | JE2 | ORD/000184/2022-2023 | 1487/SWD-I | 28/09/2022 | 27/12/2022 | MAA LAXMI ENTERPRISE | 119.84 | 85.88 | 71.67 | 90
12 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 09/12/2023 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 15
13 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Laying rising main & additional pipeline for distribution system, construction of boundary walls for 1st & 2nd Tubewell sites and other allied works for proposed ground water based ALIPORE PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11493) |  |  | ORD/000274/2024-2025 | 2924/SWD-I | 25/06/2024 | 09/08/2024 | MAA LAXMI ENTERPRISE | 67.93 | 0 | 0 | 0
Total | [13 empty] | 402.17 | 106.76 | 26.55