## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 01/11/2022] | AE SWSD-II | JE4 | ORD/000316/2022-2023 | 1470/SWD-I | 27/09/2022 | 26/03/2023 | NIRMAL UDYOG | 0.86 | 0.71 | 82.94 | 50
2 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed PANAKUA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 993] | AE SWSD-II | JE1 | ORD/000148/2022-2023 | 1388/SWD-I | 21/09/2022 | 20/12/2022 | NIRMAL UDYOG | 139.04 | 106.08 | 76.3 | 94
3 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Preparation and submission of Detailed Project Report of PANAKUA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000223/2021-2022 | 1970/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.69 | 2.54 | 94.52 | 100
4 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for PANAKUA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II |  | ORD/000028/2022-2023 | 912/SWD-I | 19/07/2022 | 18/08/2022 | SIMPLEX DRILLING CO. | 14.2 | 13.42 | 94.49 | 100
5 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 1583/SWD-I | 17/10/2022 | 17/10/2022 | Resource Division | 6.06 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Panakua water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000543/2022-2023 | 474/SMD | 20/02/2023 | 01/01/2026 | KARUNAMOY ENGINEERING | 26.42 | 12.78 | 48.37 | 70
7 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 15/08/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
8 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of PANAKUA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11494) | AE SWSD-II | JE1 | ORD/000428/2022-2023 | 2573/SWD-I | 10/01/2023 | 11/03/2023 | GOUTAM MAZUMDER | 6.05 | 5.77 | 95.38 | 100
9 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for PANAKUA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011229] | AE SWSD-II | JE1 | ORD/000594/2022-2023 | 3114/SWD-I | 24/02/2023 | 01/12/2024 | DEBASHIS DAS | 15.88 | 0 | 0 | 98
10 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Land Development of Head work site (1st tube well) in connection with Ground Water Based PANAKUA Piped Water Supply Scheme to accomodation FHTC in Bishnupur-I Block under South 24 Pgs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. [TSM/011229] | AE SWSD-II | JE1 | ORD/000808/2022-2023 | 3700/SWD-I | 30/03/2023 | 14/04/2023 | SIMPLEX DRILLING COMPANY | 0.96 | 0.96 | 99.81 | 100
11 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 28.03 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00024/2023-2024 | BP-2023-24-44 | 18/05/2023 | 18/05/2023 | WBSEDCL | 4.22 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Construction of boundary wall, approach road, pump house, additional laying of pipeline and other allied works for PANAKUA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11494] |  |  | ORD/000269/2024-2025 | 2918/SWD-I | 25/06/2024 | 09/08/2024 | NIRMAL UDYOG | 66.18 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Construction of temporary approach road, land development and allied works related to the 2nd Tubewell site of Panakua PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte. South 24 Parganas District [SM/11494] |  |  | ORD/001073/2024-2025 | 5341/SWD-I | 30/12/2024 | 29/01/2025 | DEBASHIS DAS | 5.13 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Upgradation of the outdoor illumination arrangement with other allied works at P.H. No. - 1 under Panakua Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur- I)(SM/11494) | Assistant Engineer -II | Junior Engineer | ORD/002456/2023-2024 | 185-AE-II-SMD | 20/02/2024 | 06/03/2024 | SOHINI ENTERPRISE | 0.75 | 0.75 | 100 | 100
16 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Providing bullah pilling works and other allied works for the construction of the Boundary Wall at 1st Tubewell site of Panakua PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte. [SM/11494] | AE S24D1,AE SWSD-II | JE1 | ORD/000002/2025-2026 | 905/SWD-I | 02/04/2025 | 02/05/2025 | CONCORD PROJECTS PRIVATE LIMITED | 4.07 | 0 | 0 | 99
17 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based PANAKUA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11494 | New | Payment of quotation for new service connection at Panakua PWSS, PH No-2 under Bishnupur-I Block. Application No- 1008268390 Reference Id- 106861516 Quotation Date-12/12/2024 Memo No- 1008268390/Quot/03 |  |  | BILL/02488/2024-2025 | BP-2024-25-542 | 24/01/2025 | 24/01/2025 | WBSEDCL | 5.35 | 0 | 0 | 0
Total | [13 empty] | 431.36 | 143.01 | 33.15