## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Preparation and submission of Detailed Project Report of NARAYANITALA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000216/2021-2022 | 1966/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.63 | 95.25 | 100
2 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Construction of 02 (Two) nos. chlorination rooms at Narayanitala of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD |  | ORD/000378/2022-2023 | 2212/SWD-I | 13/12/2022 | 11/02/2023 | KHAN ENTERPRISE | 11.52 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | S24 Pgns Mechanical | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Narayani Tala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000537/2022-2023 | 464/SMD | 17/02/2023 | 18/05/2023 | SWAPAN ENTERPRISE | 23.3 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Material Requisition To Resource Division |  |  | RTOR000263/2023-2024 | 2425/SWD-I | 30/09/2023 |  | Resource Division | 44.41 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Material Requisition To Resource Division |  |  | RTOR000341/2023-2024 | 262/SWD-I | 10/01/2024 |  | Resource Division | 9.41 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at NARAYANITALA Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1527) | AE BSD | JE RWS,JE-2 | ORD/000270/2022-2023 | 1800/SWD-I | 09/11/2022 | 05/09/2023 | PATH MAKERS | 382.32 | 288.11 | 75.36 | 90
7 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Additional laying of pipeline for NARAYANITALA Pipe Water Supply Scheme of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (TSM / 011225) | AE BSD | JE-2 | ORD/000404/2023-2024 | 1913/SWD-I | 21/08/2023 | 20/10/2023 | A.B. ASSOCIATES | 19.49 | 9.39 | 48.18 | 70
8 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for NARAYANITALA PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD | JE RWS,JE-2 | ORD/000078/2022-2023 | 1189/SWD-I | 02/09/2022 | 02/10/2022 | VISHAL CONSTRUCTION CO. | 28.53 | 14.22 | 49.84 | 100
9 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | S24 Pgns Mechanical | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Charges for new service connection at pump house no-1 of Narayanitala. |  |  | BILL/01154/2024-2025 | BP-2024-25-235 | 08/08/2024 |  | WBSEDCL | 17.87 | 0 | 0 | null
10 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | S24 Pgns Mechanical | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Charges for new service connection at pump house no-1 of Narayanitala. |  |  | BILL/01154/2024-2025 | BP-2024-25-235 | 08/08/2024 |  | WBSEDCL | 17.87 | 0 | 0 | null
11 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Narayanitala PWSS of BaruipurBlock for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011225] | AE BSD | JE RWS,JE-2 | ORD/000006/2023-2024 | 28/SWD-I | 05/04/2023 | 20/04/2023 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.13 | 1.5 | 48.11 | 100
12 | SOUTH 24 PARAGANAS | Baruipur,Jaynagar - I | South 24 Pgs W/S Division I | Proposed ground water based NARAYANI TALA piped water supply scheme to accommodate FHTC in JAYNAGAR-I & BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11495 | New | Construction of boundary wall and platform for providing FHTC for Ground water based NARAYANITALA piped water supply scheme to accommodate FHTC in Jaynagar-I & BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11495) |  |  | ORD/000439/2024-2025 | 3884/SWD-I | 03/09/2024 | 18/10/2024 | AYUSH ENTERPRISE | 48.14 | 0 | 0 | 0
Total | [13 empty] | 608.75 | 315.85 | 51.89