## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Preparation and submission of Detailed Project Report of "BIJOYRAMPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000397/2022-2023 | 460/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.55 | 2.51 | 98.55 | 100
2 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for BIJOYRAMPURPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II | JE2 | ORD/000033/2022-2023 | 917/SWD-I | 19/07/2022 | 18/08/2022 | SIMPLEX DRILLING CO. | 14.2 | 12.08 | 85.11 | 100
3 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Development of low land and temporary aproach road for entering Tubewell site for proposed BIJOYRAMPUR Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011224] | AE SWSD-II | JE2 | ORD/000809/2022-2023 | 3701/SWD-I | 30/03/2023 | 14/04/2023 | SIMPLEX DRILLING COMPANY | 0.95 | 0.68 | 72.16 | 100
4 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Supply & delivery of Submersible Pumping Machinery for Bijoyrampur w/s scheme under SMD, PHE Dte. |  |  | ORD/001059/2023-2024 | ...789/AE-II/SMD | 17/07/2023 | 01/08/2023 | KARUNAMOY ENGINEERING | 0.96 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Land Development at Bijoyrampur PWSS Tubewell site (Bahadurpur) in the Arsenic affected areas of South 24 pgs. Dist in Bishnupur-I Block under South 24 pgs W/S Division-I, P.H.E Dte. [TSM/011224] | AE SWSD-II |  | ORD/000244/2023-2024 | 1486/SWD-I | 19/07/2023 | 03/08/2023 | MAA LAXMI ENTERPRISE | 3.81 | 3.78 | 99.46 | 100
6 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1583/SWD-I | 17/10/2022 | 17/10/2022 | Resource Division | 5.06 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 26.06 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00703/2023-2024 | BP-2023-24-103 | 04/07/2023 | 04/07/2023 | WBSEDCL | 8.18 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bijoyrampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000542/2022-2023 | 473/SMD | 20/02/2023 | 21/05/2023 | KARUNAMOY ENGINEERING | 26.11 | 11.53 | 44.16 | 50
10 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 16/11/2025 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
11 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Supplying and fitting fixing of LED Glow sign board, betterment of external lighting arrangement etc. at P.H. No. - 1 under Bijoyrampur Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/11496) | Assistant Engineer -II | Junior Engineer | ORD/000725/2024-2025 | 1035/AE-II/SMD | 13/08/2024 | 28/08/2024 | PS & ASSOCIATES | 0.78 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed BIJOYRAMPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 821] | AE SWSD-II | JE2 | ORD/000150/2022-2023 | 1390/SWD-I | 21/09/2022 | 20/12/2022 | JAYANTA KUMAR DEY | 107.26 | 105.12 | 98 | 95
13 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of BIJOYRAMPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11496) | AE SWSD-II | JE2 | ORD/000445/2022-2023 | 2664/SWD-I | 18/01/2023 | 19/03/2023 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 6.05 | 5.86 | 96.92 | 100
14 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BIJOYRAMPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011224] | AE SWSD-II | JE2 | ORD/000508/2022-2023 | 2906/SWD-I | 14/02/2023 | 01/03/2023 | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 100 | 100
15 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Bijoyrampur PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11496) | AE SWSD-II | JE2 | ORD/000248/2024-2025 | 2668/SWD-I | 07/06/2024 | 22/07/2024 | TIYASHA ENTERPRISE | 81.5 | 0 | 0 | 15
16 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for BIJOYRAMPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011224] | AE SWSD-II | JE2 | ORD/000591/2022-2023 | 3111/SWD-I | 24/02/2023 | 01/02/2025 | DEBASHIS DAS | 15.89 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Supply & delivery of additional materials for PH No-1 of Bijoyrampur water supply scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(Block-Bishnupur-I) [SM/11496] | Assistant Engineer -II | Junior Engineer | ORD/000363/2024-2025 | 868-AE-II-SMD | 18/07/2024 | 02/08/2024 | KARUNAMOY ENGINEERING | 0.29 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based BIJOYRAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11496 | New | Payment of Quotation for new service connection at Bijoyrampur PWSS PH No- 2 under Bishnupur-I Block. Application No- 1008481333 Reference ID- 107007013 Memo No- 1008481333/Quot/03 |  |  | BILL/00363/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 3.62 | 0 | 0 | 0
Total | [13 empty] | 411.64 | 143.17 | 34.78