## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JAYATALA Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1419) | AE BSD | JE RWS,JE-2 | ORD/000272/2022-2023 | 1805/SWD-I | 09/11/2022 | 27/04/2025 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 415.42 | 53.57 | 12.9 | 50
2 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Construction of 02 (Two) nos. chlorination rooms at Jayatala at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE-1 | ORD/000360/2022-2023 | 2203/SWD-I | 13/12/2022 | 11/02/2023 | KHAN ENTERPRISE | 11.52 | 9.74 | 84.56 | 100
3 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Preparation and submission of Detailed Project Report of JOYATALA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000219/2021-2022 | 1941/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.72 | 98.77 | 100
4 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JAYATALA PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD |  | ORD/000075/2022-2023 | 1186/SWD-I | 02/09/2022 | 02/10/2022 | TAPAS KUMAR GIRI | 28.52 | 24.79 | 86.92 | 100
5 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 1574/SWD-I | 16/10/2022 | 16/10/2022 | Resource Division | 8.74 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of JAYATALA PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [SM/11501] |  |  | ORD/000551/2023-2024 | 2499/SWD-I | 06/10/2023 | 21/10/2023 | TAPAS KUMAR GIRI | 3.14 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jaytala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000536/2022-2023 | 463/SMD | 17/02/2023 | 18/05/2023 | SWAPAN ENTERPRISE | 23.3 | 22.22 | 95.4 | 100
8 | SOUTH 24 PARGANAS | Baruipur | South 24 Pgs W/S Division I | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 2.66 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01501/2023-2024 | BP-2023-24-182 | 02/08/2023 | 02/08/2023 | WBSEDCL | 2.61 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00007/2023-2024 | BP-2023-24-43 | 18/05/2023 | 18/05/2023 | WBSEDCL | 3.43 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Jaytala W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | Assistant Engineer | Junior Engineer | ORD/002476/2023-2024 | 265/SMSD | 23/02/2024 | 09/03/2024 | SWAPAN ENTERPRISE | 0.89 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Supply & installation of Vinyl printing ACP board at Head work site of Jayatala ,Jelerhat & kuruli water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- SONARPUR ] | Assistant Engineer | Junior Engineer | ORD/001557/2024-2025 | 567/SMSD | 07/05/2024 | 22/05/2024 | S.S. SIGNS | 0.89 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Jaytala scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11501) | Assistant Engineer | Junior Engineer | ORD/002798/2023-2024 | 384-SMSD | 28/03/2024 | 12/04/2024 | SWAPAN ENTERPRISE | 0.89 | 0.88 | 99.6 | 100
14 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of of Joytala W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11501) | Assistant Engineer | Junior Engineer | ORD/002797/2023-2024 | 383/SMSD | 28/03/2024 | 12/04/2024 | SWAPAN ENTERPRISE | 0.58 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Baruipur | S24 Pgns Mechanical | Ground water based JAYTALA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11501 | New | Supply, delivery stand by submersible pump for Jaytal W/S Scheme under SMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001596/2024-2025 | 294/SMSD | 28/02/2025 | 15/03/2025 | S.S.G ENTERPRISE | 0.82 | 0 | 0 | 100
Total | [13 empty] | 506.15 | 113.93 | 22.51