## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for LAKSHMIKANTAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II | JE4 | ORD/000029/2022-2023 | 913/SWD-I | 19/07/2022 | 18/08/2022 | SIMPLEX DRILLING CO. | 14.19 | 12.22 | 86.12 | 100
2 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Preparation and submission of Detailed Project Report of LAKSHMIKANTAPUR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000230/2021-2022 | 1979/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.55 | 2.52 | 98.79 | 100
3 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 3249/SWD-I | 01/03/2023 |  | Resource Division | 25.56 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for LAKSHMIKANTAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE SWSD-II | JE4 | ORD/000860/2022-2023 | 2963/SWD-I | 16/02/2023 | 03/03/2023 | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 100 | 0
5 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01059/2023-2024 | BP-2023-24-125 | 17/07/2023 |  | WBSEDCL | 6.17 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of LAKSHMIKANTAPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11502) | AE SWSD-II |  | ORD/000442/2022-2023 | 2661/SWD-I | 18/01/2023 | 19/03/2023 | M/S P. PURKAIT ENTERPRISE. | 6.02 | 2.92 | 48.59 | 100
7 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1583/SWD-I | 17/10/2022 |  | Resource Division | 5.74 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.06.2023 to 30.11.2023] |  |  | ORD/000176/2023-2024 | 778/SWD-I | 31/05/2023 | 27/11/2023 | PUSPA JAISWAL | 0.87 | 1.84 | 211.29 | 40
9 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Laying of HDPE pipe from Second Tubewell to distribution network under Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. [SM Code: TSM/011195, SM/11502] | AE SWSD-II | JE4 | ORD/000669/2023-2024 | 3020/SWD-I | 30/11/2023 | 29/01/2024 | MS MANABESH ROY | 24.39 | 9.64 | 39.51 | 98
10 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Lakshmikantapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000539/2022-2023 | 470/SMD | 20/02/2023 | 21/05/2023 | AHALYA ENGINEERING WORKS | 26.92 | 11.59 | 43.06 | 50
11 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.12.2023 to 31.05.2024] [Vehicle No- WB-04G-7357] | AE S24D1 | JE-2 | ORD/000700/2023-2024 | 2924/SWD-I | 23/11/2023 | 24/05/2024 | PUSPA JAISWAL | 0.87 | 1.92 | 221.04 | 30
12 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Lakshikantapur PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte, South 24-Pgns disct. (SM/11502) |  |  | ORD/000270/2024-2025 | 2920/SWD-I | 25/06/2024 | 09/08/2024 | NIKHIL SAMADDAR | 39.42 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed LAKSHMIKANTAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 932] | AE SWSD-II | JE4 | ORD/000149/2022-2023 | 1389/SWD-I | 21/09/2022 | 20/12/2022 | MS MANABESH ROY | 111.29 | 73.58 | 66.11 | 95
14 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 09/12/2023 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
15 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Lakshmikantapur Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11502] | Assistant Engineer -II | Junior Engineer | ORD/002374/2023-2024 | 984-AE-II-SMD | 13/09/2023 | 28/09/2023 | AHALYA ENGINEERING WORKS | 0.58 | 0.58 | 100 | 100
16 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Supply & Delivery of Submersible Pumping Machinery for PH No.-1 of Lakshmikantapur Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11502] | Assistant Engineer -II | Junior Engineer | ORD/002453/2023-2024 | 963-AE-II-SMD | 07/09/2023 | 22/09/2023 | AHALYA ENGINEERING WORKS | 0.89 | 0.15 | 17.41 | 100
17 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.06.2024 to 30.11.2024] [Vehicle No- WB-04G-7357] | AE HQ-II,AE S24D1 | JE-2 | ORD/000198/2024-2025 | 2356/SWD-I | 24/05/2024 | 23/11/2024 | PUSPA JAISWAL | 0.87 | 0.38 | 44.22 | 0
18 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11502 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for LAKSHMIKANTAPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011195] | AE SWSD-II | JE4 | ORD/000587/2022-2023 | 3108/SWD-I | 24/02/2023 | 26/03/2023 | MOULI CONSTRUCTION | 15.87 | 0 | 0 | 0
Total | [13 empty] | 390.59 | 118.94 | 30.45