## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for DOSATINA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II | JE4 | ORD/000030/2022-2023 | 914/SWD-I | 19/07/2022 | 18/08/2022 | SIMPLEX DRILLING CO. | 14.2 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Preparation and submission of Detailed Project Report of "DOSTINA Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000403/2022-2023 | 457/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.51 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DOSATINA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011196] | AE SWSD-II | JE4 | ORD/000506/2022-2023 | 2904/SWD-I | 14/02/2023 | 01/03/2023 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Development of low land and temporary aproach road for entering Tubewell site for proposed DOSATINA Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011196] | AE SWSD-II | JE4 | ORD/000807/2022-2023 | 3699/SWD-I | 30/03/2023 | 14/04/2023 | SIMPLEX DRILLING COMPANY | 0.96 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of DOSATINA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11503) | AE SWSD-II |  | ORD/000444/2022-2023 | 2663/SWD-I | 18/01/2023 | 19/03/2023 | M/S P. PURKAIT ENTERPRISE. | 6.02 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1583/SWD-I | 17/10/2022 | 17/10/2022 | Resource Division | 5.69 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Material Requisition To Resource Division |  |  | RTOR000109/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 23.65 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02494/2023-2024 | BP-2023-24-265 | 18/09/2023 | 18/09/2023 | WBSEDCL | 4.93 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dosatina water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000540/2022-2023 | 471/SMD | 20/02/2023 | 21/05/2023 | AHALYA ENGINEERING WORKS | 26.92 | 0 | 0 | 40
10 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 16/11/2025 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
11 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for DOSATINA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011196] | AE SWSD-II | JE4 | ORD/000385/2023-2024 | 1821/SWD-I | 16/08/2023 | 15/09/2023 | MOULI CONSTRUCTION | 15.87 | 0 | 0 | 70
12 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Supplying and fitting fixing of LED Glow sign board, betterment of external lighting arrangement etc. at P.H. No. 1 under Dosatina Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I) (SM/11503) | Assistant Engineer -II | Junior Engineer | ORD/002510/2023-2024 | 209-AE-II-SMD | 28/02/2024 | 14/03/2024 | BHUNIA BUILDERS | 0.75 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Dosatina Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11503] | Assistant Engineer -II | Junior Engineer | ORD/002370/2023-2024 | 1378-AE-II-SMD | 14/12/2023 | 29/12/2023 | AHALYA ENGINEERING WORKS | 0.56 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed DOSATINA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 924] | AE SWSD-II | JE4 | ORD/000187/2022-2023 | 1489/SWD-I | 28/09/2022 | 25/06/2025 | NEW STAR CONSTRUCTION | 110.18 | 0 | 0 | 70
15 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based DOSATINA piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11503 | New | Construction of boundary wall, pump house, laying of additional pipeline, and other allied works for DOSATINA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11503] | AE SWSD-II | JE4 | ORD/000258/2024-2025 | 2675/SWD-I | 07/06/2024 | 31/08/2025 | NEW STAR CONSTRUCTION | 43.67 | 0 | 0 | 85
Total | [13 empty] | 364.3 | 0 | 0