## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of 10 nos. Portable Tower System, Brand HP, Model HP 280 pro G6 Microtower PC i7 |  |  | BILL/00027/2022-2023 | BP-2022-23-121 | 20/12/2022 | 20/12/2022 | IONET | 9.5 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of Microtek Line interactive UPS |  |  | BILL/01500/2023-2024 | BP-2023-24-506 | 28/11/2023 | 28/11/2023 | IONET | 0.18 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of Intel Core i5 12500 computer - 5 nos. |  |  | BILL/01502/2023-2024 | BP-2023-24-507 | 28/11/2023 | 28/11/2023 | MS EASY DAY ENTERPRISE | 3.16 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of Canon make digital plain paper copier Model IR-2725+DADF with NPG 87 toner |  |  | BILL/01481/2023-2024 | BP-2023-24-496 | 23/11/2023 | 23/11/2023 | SOMATRONICS | 4.2 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of Brother Multifunction machines MFM |  |  | BILL/01499/2023-2024 | BP-2023-24-506 | 28/11/2023 | 28/11/2023 | IONET | 0.43 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of Microtek Line Interactive UPS |  |  | BILL/00157/2022-2023 | BP-2022-23-174 | 18/01/2023 | 18/01/2023 | DIGITEK SOLUTIONS | 0.31 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of HP Intel core i7 14 inch Laptop |  |  | BILL/01501/2023-2024 | BP-2023-24-506 | 28/11/2023 | 28/11/2023 | IONET | 0.88 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Procurement of Canon MAXIFY GX2070 colour A4 printer through GEM |  |  | BILL/00765/2024-2025 | BP-2024-25-484 | 28/10/2024 | 28/10/2024 | MARUTI ENTERPRISE | 0.21 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of Brother Multifunction machines MFM through eGEM |  |  | BILL/00441/2024-2025 | BP-2024-25-301 | 11/09/2024 | 11/09/2024 | IONET | 0.5 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Procurement of Printer Canon 230V Multifunction MF244DW through GEM |  |  | BILL/00731/2024-2025 | BP-2024-25-466 | 06/10/2024 | 06/10/2024 | MARUTI ENTERPRISE | 0.5 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Procurement of Desk top computer make hp Intel Core i7 12700 16 GB/ 1000 GB HDD/ Windows 11 Professional |  |  | BILL/00797/2024-2025 | BP-2024-25-495 | 21/11/2024 | 21/11/2024 | MS EASY DAY ENTERPRISE | 2.85 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Procurement of Photocopier machine make CANON IR 2928 with DADF with platten cover & NPG Toner Sl No.-4QE05967 DADF Sl No. - F281350 |  |  | BILL/00842/2024-2025 | BP-2024-25-503 | 10/12/2024 | 10/12/2024 | SOMATRONICS | 1.89 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of HP 53.5 - 55.5 CM Liquid Crystal Display LCD Panel or Monitors |  |  | BILL/00439/2024-2025 | BP-2024-25-301 | 11/09/2024 | 11/09/2024 | IONET | 0.18 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of Microtek Line Interactive UPS with AVR of Rating 0.65 KVA With Warranty of 2 Years |  |  | BILL/00440/2024-2025 | BP-2024-25-301 | 11/09/2024 | 11/09/2024 | IONET | 0.21 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Supply of HP intel Core i5 13500 16 GB/0 GB HDD/ Windows 11Professional Model: HP i5 Desktop PC |  |  | BILL/00438/2024-2025 | BP-2024-25-301 | 11/09/2024 | 11/09/2024 | IONET | 2.85 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | PROCUREMENT OF HP MID LEVEL DESKTOP COMPUTER WITH 3 YEARS WARRANTY |  |  | BILL/01150/2024-2025 | BP-2024-25-609 | 27/03/2025 | 27/03/2025 | IONET | 0.73 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Procurement of Multifunction Machine MFM (V2) (Q2) [ CANON IR 2945 WITH DADF AND TONER] |  |  | BILL/01149/2024-2025 | BP-2024-25-608 | 27/03/2025 | 27/03/2025 | SOMATRONICS | 6.8 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Improvement of IT infrastructure by providing Desktop computers, printers, copiers and its peripherals for different water testing laboratories and division & Sub division offices under South 24 Pargana W/S Division - I, P.H.E Dte. | SM/11637 | Support-MIS | Procurement one no UPS 650VA |  |  | BILL/01151/2024-2025 | BP-2024-25-609 | 27/03/2025 | 27/03/2025 | IONET | 0.03 | 0 | 0 | 0
Total | [13 empty] | 35.41 | 0 | 0