## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Preparation and submission of Detailed Project Report of SITAKUNDU(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000450/2021-2022 | 1949/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.62 | 95.07 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 11.9 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Payment of Electric Bill for new service connection under SMD PHE Dte. |  |  | BILL/00285/2023-2024 | BP-2023-24-20 | 15/05/2023 | 15/05/2023 | WBSEDCL | 5.93 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for SITAKUNDU (ZONE-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD | JE RWS | ORD/000080/2022-2023 | 1191/SWD-I | 02/09/2022 | 02/10/2022 | TAPAS KUMAR GIRI | 40.13 | 16.45 | 40.98 | 50
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at SITAKUNDU (Zone-I) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1753) | AE BSD | JE RWS | ORD/000230/2022-2023 | 1691/SWD-I | 01/11/2022 | 28/08/2023 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 379.75 | 171.29 | 45.11 | 80
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of SITAKUNDU (Zone-I) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [SM/11645] | AE BSD | JE RWS | ORD/000552/2023-2024 | 2500/SWD-I | 06/10/2023 | 21/10/2023 | TAPAS KUMAR GIRI | 4.41 | 2.2 | 50 | 100
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Construction of platform for FHTC, restoration of road after laying of pipeline, development of land and other allied works for "Ground Water Based SITAKUNDU (ZONE -I) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/11645) |  |  | ORD/000524/2024-2025 | 4017/SWD-I | 13/09/2024 | 12/11/2024 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 84.63 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00127/2024-2025 | BP-2024-25-41 | 24/04/2024 | 24/04/2024 | WBSEDCL | 9.22 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Sitakundu (Zone-I)at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE RWS | ORD/000363/2022-2023 | 2206/SWD-I | 13/12/2022 | 19/07/2024 | JOY GURU TRADING | 11.52 | 4.74 | 41.2 | 50
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Sitakundu water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000446/2022-2023 | 3926/SMD | 30/12/2022 | 01/06/2025 | M/S.UTTAM KUMAR CHATTERJEE | 22.38 | 0 | 0 | 40
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Sitakundu (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11645) | Assistant Engineer | Junior Engineer | ORD/001592/2024-2025 | 100/SMSD | 21/01/2025 | 05/02/2025 | M/S.UTTAM KUMAR CHATTERJEE | 0.91 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for SITAKUNDU ZONE-I Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11645] |  |  | ORD/000028/2025-2026 | 1061/SWD-I | 22/04/2025 | 22/05/2025 | MONDAL TUBEWELL | 15.82 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Sitakundu (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11645) | Assistant Engineer | Junior Engineer | ORD/001594/2024-2025 | 98/SMSD | 21/01/2025 | 05/02/2025 | M/S.UTTAM KUMAR CHATTERJEE | 0.58 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Supply & installation of Vinyl printing ACP board at Head work site of Sitakundu(Zone-I),Srinagar & Hogalkuria water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- SONARPUR ] | Assistant Engineer | Junior Engineer | ORD/001553/2024-2025 | 561/SMSD | 03/05/2024 | 18/05/2024 | S.S. SIGNS | 0.89 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-I piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11645 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Sitakundu (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11645) | Assistant Engineer | Junior Engineer | ORD/001593/2024-2025 | 99/SMSD | 21/01/2025 | 05/02/2025 | M/S.UTTAM KUMAR CHATTERJEE | 0.91 | 0 | 0 | 100
Total | [13 empty] | 591.73 | 197.31 | 33.34