## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for SITAKUNDU (ZONE-II) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD |  | ORD/000079/2022-2023 | 1190/SWD-I | 02/09/2022 | 02/10/2022 | TAPAS KUMAR GIRI | 40.13 | 37.11 | 92.47 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Sitakundu (Zone-II) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD |  | ORD/000361/2022-2023 | 2204/SWD-I | 13/12/2022 | 11/02/2023 | JOY GURU TRADING | 11.52 | 9.49 | 82.36 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Preparation and submission of Detailed Project Report of SITAKUNDU(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000444/2021-2022 | 1950/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.63 | 95.44 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 11.9 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Sitakundu water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000447/2022-2023 | 3927/SMD | 30/12/2022 | 30/03/2023 | M/S.UTTAM KUMAR CHATTERJEE | 22.38 | 20.41 | 91.22 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Supply & Installation of LED board at P.H. No-1 & 2 of Sitakundu (Zone-II) water supply scheme, under South 24-pgs Mechanical Division PHE Dte. [Block-Baruipur] |  |  | ORD/001632/2023-2024 | 1071/SMSD | 17/08/2023 | 27/08/2023 | M/S.UTTAM KUMAR CHATTERJEE | 0.78 | 0.78 | 100 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Improvement of Outdoor illumination arrangement with allied works at PH-1, Zone-II of Sitakundu water supply scheme under SMD, PHE Dte. (Block- Baruipur) |  |  | ORD/002573/2023-2024 | .1060/SMSD | 10/08/2023 | 25/08/2023 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0.88 | 100 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Improvement of Outdoor illumination arrangement with allied works at PH-2, Zone-II of Sitakundu water supply scheme under SMD, PHE Dte. (Block- Baruipur) |  |  | ORD/002574/2023-2024 | .1061/SMSD | 10/08/2023 | 25/08/2023 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0.88 | 100 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | 1) L027-Sagarsangha Math on T03 to Dudhnai(WB/02/480) 2) Construction of Road from Fultala Chow More to Block-A, B.C,D to Ramkrisna Polly to Mohamonilala Greater Kolkata Enginnering College to Ramnagar Bazar via Dhapdhopi road Shakharipukur under Baruipur Block. |  |  | BILL/01677/2024-2025 | BP-2024-25-782 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.88 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work , cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. |  |  | BILL/00759/2024-2025 | BP-2024-25-451 | 06/10/2024 | 06/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 12 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SITAKUNDU [Zone-II] PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11646] | AE BSD | JE-1 | ORD/000806/2023-2024 | 1289/SWD-I | 15/03/2024 | 30/03/2024 | TAPAS KUMAR GIRI | 4.41 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Construction of boundary walls with land development and other allied works for Ground Water Based SITAKUNDU (Zone-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/11646) | AE BSD | JE-1 | ORD/000847/2023-2024 | 1252/SWD-I | 13/03/2024 | 12/11/2025 | BAIDYA ENTERPRISE | 49.19 | 0 | 0 | 51
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Supply, delivery stand by submersible pump for Sitakundu (Zone-II) W/S Scheme under SMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 1117/SMSD | 06/08/2024 | 21/08/2024 | MAA SARADA CONSTRUCTION | 0.81 | 0.81 | 100 | 100
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SITAKUNDU ZONE-II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11646 | Augmentation | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at SITAKUNDU (Zone-II) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1753) | AE BSD | JE-1 | ORD/000234/2022-2023 | 1710/SWD-I | 02/11/2022 | 01/01/2026 | M/S R.K. ENTERPRISE | 372.96 | 129.32 | 34.67 | 80
Total | [13 empty] | 531.48 | 202.32 | 38.07