## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for KAMARIA (ZONE-III) PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD |  | ORD/000083/2022-2023 | 1194/SWD-I | 02/09/2022 | 02/10/2022 | AYUB KHAN | 37.76 | 4.28 | 11.34 | 10
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation along with Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KAMARIA (ZONE-III) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2051) | AE BSD | JE-1 | ORD/000279/2022-2023 | 1840/SWD-I | 11/11/2022 | 01/04/2025 | MANASH GHOSH | 391.21 | 112.4 | 28.73 | 45
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Kamaria (Zone-III) of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE-1 | ORD/000380/2022-2023 | 2214/SWD_I | 13/12/2022 | 02/12/2024 | ALISHA CONSTRUCTION | 11.52 | 9.95 | 86.38 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kamaria Zone-III PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011003] | AE BSD |  | ORD/000732/2022-2023 | 3582/SWD-I | 22/03/2023 | 06/04/2023 | AYUB KHAN | 4.35 | 0.14 | 3.18 | 10
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamaria Zone-III water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000571/2022-2023 | 590/SMD | 24/02/2023 | 01/05/2025 | AHALYA ENGINEERING WORKS | 22.93 | 0 | 0 | 45
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 23.23 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Construction of protection work for pipeline, approach road, development of land and other allied works for KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district.(SM/11647) |  |  | ORD/000224/2024-2025 | 2642/SWD-I | 07/06/2024 | 22/07/2024 | AYUSH ENTERPRISE | 16.77 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11647 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 & 2 of Kamaria Zone-III W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/11647) | Assistant Engineer | Junior Engineer | ORD/002463/2024-2025 | 1535/SMSD | 19/11/2024 | 01/02/2025 | AHALYA ENGINEERING WORKS | 0.61 | 0 | 0 | 100
Total | [13 empty] | 508.39 | 126.77 | 24.94