## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Preparation and submission of Detailed Project Report of "KAIKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000409/2022-2023 | 466/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.55 | 2.55 | 100 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 3249/SWD-I | 01/03/2023 |  | Resource Division | 32.27 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KAIKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11730) | AE SWSD-II | JE4 | ORD/000433/2022-2023 | 2577/SWD-I | 10/01/2023 | 11/03/2023 | N&N ENTERPRISE | 6.04 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KAIKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011788] | AE SWSD-II | JE4 | ORD/000521/2022-2023 | 2911/SWD-I | 14/02/2023 | 01/03/2023 | M/S PURE RENOVATION CONSTRUCTION GROUP (EMAIL ID-SAJIDMOLLA93@GMAIL.COM) | 1.57 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for KAIKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011788] | AE SWSD-II | JE4 | ORD/000553/2022-2023 | 3043/SWD-I | 20/02/2023 | 22/03/2023 | TAPAS KUMAR GIRI | 15.9 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kaikhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000486/2022-2023 | 239/SMD | 24/01/2023 | 24/04/2023 | M/S. PS & ASSOCIATES | 25.92 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KAIKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 790 nos.] | AE SWSD-II | JE4 | ORD/000447/2022-2023 | 2685/SWD-I | 20/01/2023 | 20/04/2023 | M/S BIMALENDU BOSE | 122.59 | 76.13 | 62.1 | 50
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KAIKHALI PWSS of BISHNUPUR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11730] |  |  | ORD/000784/2023-2024 | 1067/SWD-I | 04/03/2024 | 19/03/2024 | SAIKAT ENTERPRISE | 1.57 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KAIKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11730] | AE SWSD-II | JE4 | ORD/000585/2023-2024 | 2753/SWD-I | 07/11/2023 | 07/12/2023 | SAIKAT ENTERPRISE | 15.03 | 0 | 0 | 20
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Kaikhali PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11730) | AE SWSD-II | JE4 | ORD/000267/2024-2025 | 2682/SWD-I | 07/06/2024 | 22/07/2024 | SHRAYA ROADS LINE. | 52.47 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based KAIKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11730 | Augmentation | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 09/12/2023 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
Total | [13 empty] | 382.7 | 78.68 | 20.56