## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for PIRKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11731] | AE SWSD-II | JE3 | ORD/000173/2022-2023 | 1448/SWD-I | 26/09/2022 | 26/10/2022 | SUBHRA ENTERPRISE | 14.27 | 13.9 | 97.47 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Preparation and submission of Detailed Project Report of PIRKHALI AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000232/2021-2022 | 1977/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.61 | 94.68 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PIRKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011789] | AE SWSD-II | JE3 | ORD/000519/2022-2023 | 2909/SWD-I | 14/02/2023 | 01/03/2023 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 100 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of PIRKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11731) (2nd Call) | AE SWSD-II | JE3 | ORD/000110/2023-2024 | 517/SWD-I | 10/05/2023 | 09/07/2023 | DEBAYAN MONDAL | 5.75 | 5.56 | 96.71 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 38.38 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Payment for Electricity Bill for New connection under SMD PHE Dte. |  |  | BILL/03112/2023-2024 | BP-2023-24-327 | 16/10/2023 | 16/10/2023 | WBSEDCL | 5.29 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 16/11/2025 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Incorporation of LED Glow sign board including other allied works at PH No-1 under Pirkhali Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Bishnupur-I) (SM/11731) | Assistant Engineer -II | Junior Engineer | ORD/002462/2023-2024 | 186-AE-II-SMD | 21/02/2024 | 07/03/2024 | KUNAL ENTERPRISE | 0.75 | 0.75 | 100 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based PIRKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 815 nos.] | AE SWSD-II | JE3 | ORD/000422/2022-2023 | 2583/SWD-I | 10/01/2023 | 01/07/2025 | LOKENIRMAN | 141.2 | 123.7 | 87.6 | 100
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Pirkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000489/2022-2023 | 247/SMD | 27/01/2023 | 01/01/2026 | T.S. CONSTRUCTION | 25.93 | 12.36 | 47.69 | 70
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Construction of boundary wall, approach road, pump house, laying of pipeline and other allied works for ground water based PIRKHALI PWSS to accomodate FHTC in Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. for Augmentation of Surface water based water supply scheme in the Arsenic affected areas of South 24 Paraganas District. (SM/11731) | AE SWSD-II | JE3 | ORD/000391/2024-2025 | 3631/SWD-I | 20/08/2024 | 01/10/2025 | S.C. ENTERPRISE | 107.87 | 0 | 0 | 10
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for PIRKHALI Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11731] | AE SWSD-II | JE3 | ORD/000695/2024-2025 | 4490/SWD-I | 30/10/2024 | 26/03/2025 | B.K.ENTERPRISE | 15.88 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Pirkhali Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11731] | Assistant Engineer -II | Junior Engineer | ORD/002235/2023-2024 | 1377-AE-II-SMD | 14/12/2023 | 29/12/2023 | T.S. CONSTRUCTION | 0.4 | 0.4 | 100 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based PIRKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11731 | Augmentation | Payment of quotation for new service connection at Pirkhali PWSS, PH No-2 under Bishnupur-I Block. Application No- 1008246027 Reference Id- 106856054 Quotation Date-09/12/2024 Memo No- 1008268233/Quot/03 |  |  | BILL/02494/2024-2025 | BP-2024-25-541 | 24/01/2025 | 24/01/2025 | WBSEDCL | 12.9 | 0 | 0 | 0
Total | [13 empty] | 479.74 | 160.85 | 33.53