## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KASTHAMAHAL Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11733] | AE SWSD-II | JE4 | ORD/000175/2022-2023 | 1450/SWD-I | 26/09/2022 | 26/10/2022 | SUBHRA ENTERPRISE | 14.26 | 13.26 | 92.96 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Preparation and submission of Detailed Project Report of "KASTHA MAHAL Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000408/2022-2023 | 465/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.51 | 2.51 | 100 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KASTHAMAHAL PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011792] | AE SWSD-II | JE4 | ORD/000524/2022-2023 | 2920/SWD-I | 14/02/2023 | 01/03/2023 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 100 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method at Second Tube-well site for KASTHAMAHAL PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011792] | AE SWSD-II | JE4 | ORD/000540/2022-2023 | 3018/SWD-I | 20/02/2023 | 22/03/2023 | TAPAS KUMAR GIRI | 15.9 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KASTHAMAHAL Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11733) | AE SWSD-II | JE4 | ORD/000432/2022-2023 | 2576/SWD-I | 10/01/2023 | 11/03/2023 | R.G ENTERPRISE | 6.04 | 5.8 | 95.95 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 36.56 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01748/2023-2024 | BP-2023-24-211 | 11/08/2023 | 11/08/2023 | WBSEDCL | 4.78 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KASTHAMAHAL PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 985 nos.] | AE SWSD-II | JE4 | ORD/000498/2022-2023 | 2866/SWD-I | 09/02/2023 | 10/05/2023 | S.R ENTERPRISE (EMAIL- SOMENATH.MAJUMDER9874@GMAIL.COM) | 119.6 | 115.8 | 96.82 | 95
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kasthamahal water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000487/2022-2023 | 245/SMD | 27/01/2023 | 27/04/2023 | KARUNAMOY ENGINEERING | 26.26 | 11.39 | 43.35 | 50
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 16/11/2025 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Kasthamahal PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11733) | AE SWSD-II | JE4 | ORD/000264/2024-2025 | 2679/SWD-I | 07/06/2024 | 22/07/2024 | S.R ENTERPRISE (KARUNAMOYEE) | 50.56 | 0 | 0 | 10
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KASTHAMAHAL piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distric | SM/11733 | Augmentation | Renovation of external illumination arrangement including incorporating LED Glow sign board and other allied works at P.H. No. - 1 under Kasthamahal Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I)(SM/11733) | Assistant Engineer -II | Junior Engineer | ORD/002509/2023-2024 | 223-AE-II-SMD | 01/03/2024 | 16/03/2024 | PURUSHOTTAM ENTERPRISE | 0.75 | 0.75 | 100 | 100
Total | [13 empty] | 385.58 | 151.07 | 39.18