## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE VII -A & ZONE VII-B AT NALGORA MOUZA OF JOYNAGAR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11770 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 3000/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 73.38 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE VII -A & ZONE VII-B AT NALGORA MOUZA OF JOYNAGAR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11770 | Augmentation | Additional work for Laying distribution system at Zone-VII (NOLGORA) of JOYNAGAR-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte.(SM/ 11770 , SM/16183) | AE BSD | JE RWS | ORD/000364/2024-2025 | 3511/SWD-I | 07/08/2024 | 30/06/2025 | MRA NIRMAN UDYOG | 434.23 | 36.81 | 8.48 | 40
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | PROVIDING 100% FHTC IN ZONE VII -A & ZONE VII-B AT NALGORA MOUZA OF JOYNAGAR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR DISTRICT.- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I, P.H.E DTE. | SM/11770 | Augmentation | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-VII NOLGORA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 11912] [TSM/011554] and [TSM/015335] 124076810.5 | AE BSD | JE RWS | ORD/000260/2023-2024 | 1515/SWD-I | 21/07/2023 | 31/12/2025 | MRA NIRMAN UDYOG | 1590.17 | 102.94 | 6.47 | 65
Total | [13 empty] | 2097.77 | 139.75 | 6.66