## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JOYKRISHNA NAGAR PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD |  | ORD/000086/2022-2023 | 1197/SWD-I | 02/09/2022 | 02/10/2022 | VISHAL CONSTRUCTION CO. | 28.53 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Preparation and submission of Detailed Project Report of JOYKRISHNANAGAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000217/2021-2022 | 1939/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.76 | 100 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1983 | 25/11/2022 | 25/11/2022 | Resource Division | 11.73 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JOYKRISHNANAGAR Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1904) | AE BSD |  | ORD/000341/2022-2023 | 2091/SWD-I | 02/12/2022 | 28/09/2023 | SUPRITI ENTERPRISE | 534.05 | 184.52 | 34.55 | 40
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Joykrishnanagar of Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD |  | ORD/000376/2022-2023 | 2210/SWD-I | 13/12/2022 | 11/02/2023 | S.M ENTERPRISE | 11.49 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Joykrishnanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000450/2022-2023 | 3930/SMD | 30/12/2022 | 30/03/2023 | M/S. S.R. ENTERPRISE | 22.37 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of JOYKRISHNA NAGAR PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011093] | AE BSD |  | ORD/000457/2023-2024 | 2111/SWD-I | 30/08/2023 | 14/09/2023 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.14 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 2.38 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00003/2024-2025 | BP-2024-25-02 | 05/04/2024 | 05/04/2024 | WBSEDCL | 4.74 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based JOYKRISHNANAGAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, South 24 pgns district for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of Sout | SM/11772 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/06297/2023-2024 | BP-2023-24-648 | 30/03/2024 | 30/03/2024 | WBSEDCL | 4.68 | 0 | 0 | 0
Total | [13 empty] | 625.87 | 187.28 | 29.92