## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia& 300 mtr. deepTubewell by Rotary method for Padmerhat PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/011744] | AE BSD |  | ORD/000102/2022-2023 | 1234/SWD-I | 07/09/2022 | 07/10/2022 | SAIKAT ENTERPRISE | 28.4 | 25.67 | 90.41 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | Preparation and submission of Detailed Project Report of "PADMERHAT Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000387/2022-2023 | 469/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.65 | 2.63 | 99.41 | 100
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 295/SWD-I | 25/04/2023 |  | Resource Division | 41.81 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Padmerhat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000279/2022-2023 | 274/SMD | 01/02/2023 | 02/05/2023 | SAIKAT ENTERPRISE | 22.37 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Padmerhat PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011744] | AE BSD |  | ORD/000725/2022-2023 | 3571/SWD-I | 22/03/2023 | 06/04/2023 | SAIKAT ENTERPRISE | 3.14 | 3.14 | 100 | 0
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/00511/2023-2024 | BP-2023-24-74 | 13/06/2023 |  | WBSEDCL | 6.42 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | Balance miscellaneous work for Ground water based PADMERHAT Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/11780) |  |  | ORD/000864/2023-2024 | 1200/SWD-I | 11/03/2024 | 25/04/2024 | BENGAL BUILDERS | 53.81 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based PADMERHAT piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11780 | Augmentation | Construction of 01 No. 300 Cum. capacity OHR and 02 Nos. 350 Cum capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of JANGALIA, MASTIKARI and PADMERHAT MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 5561] | AE BSD | JE-1 | ORD/000212/2023-2024 | 1374/SWD-I | 12/07/2023 | 07/05/2024 | KAR CONSTRUCTION | 1262.63 | 84.76 | 6.71 | 20
Total | [13 empty] | 1421.21 | 116.2 | 8.18