## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for SAPHKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11781] | AE SWSD-II | JE4 | ORD/000176/2022-2023 | 1451/SWD-I | 26/09/2022 | 26/10/2022 | SUBHRA ENTERPRISE | 14.27 | 12.44 | 87.2 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based SAPHKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 868 nos.] | AE SWSD-II | JE4 | ORD/000418/2022-2023 | 2472/SWD-I | 30/12/2022 | 01/04/2025 | MERCANTILE HALL | 103.26 | 79.81 | 77.29 | 90
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Preparation and submission of Detailed Project Report of "SAPKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000399/2022-2023 | 468/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.51 | 2.51 | 100 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAPKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011741] | AE SWSD-II | JE4 | ORD/000522/2022-2023 | 2912/SWD-I | 14/02/2023 | 01/03/2023 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 100 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Saphkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000507/2022-2023 | 342/SMD | 08/02/2023 | 09/05/2023 | AHALYA ENGINEERING WORKS | 26.58 | 12.67 | 47.66 | 50
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 04/09/2026 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 40
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for SAPKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011741] | AE SWSD-II | JE4 | ORD/000584/2022-2023 | 3105/SWD-I | 24/02/2023 | 05/12/2024 | MOULI CONSTRUCTION | 15.88 | 5.1 | 32.12 | 98
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of SAPHKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11781) | AE SWSD-II | JE4 | ORD/000446/2022-2023 | 2665/SWD-I | 18/01/2023 | 19/03/2023 | M/S. TORSA ENTERPRISE | 6.04 | 5.87 | 97.17 | 100
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Repairing of R.C.C. elevated reservoir (1135 Cum capacity) of staging height 20.0 mtr. of ZONE-14 under ground water based SAPKHALI PWSS to Accommodate FHTC in Bishnupur-I Block under South 24-Pgs. W/S Divn.-I, P.H.E. Dte. for augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. [SM/11781] | AE SWSD-II | JE4 | ORD/000622/2023-2024 | 2805/SWD-I | 09/11/2023 | 24/12/2023 | NIKHIL SAMADDAR | 17.95 | 17.06 | 95.04 | 98
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 2555/SWD-I | 09/01/2023 | 09/01/2023 | Resource Division | 5.35 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 25.83 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02496/2023-2024 | BP-2023-24-264 | 18/09/2023 | 18/09/2023 | WBSEDCL | 13.97 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Construction of boundary wall, pump house, restoration of road, laying of additional pipeline and other allied works for SAPKHALI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11781] [2nd call] | AE SWSD-II | JE4 | ORD/000506/2024-2025 | 3963/SWD-I | 10/09/2024 | 11/07/2026 | SUKUMAR DEBNATH | 48 | 0 | 0 | 80
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Improvement of working ambience by providing requsite external luminaires, supplying of chair & table etc. at P.H. No. - 1 under Sapkhali Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/11781) | Assistant Engineer -II | Junior Engineer | ORD/000799/2024-2025 | 1039-AE-II-SMD | 13/08/2024 | 28/08/2024 | MONOSEBA CONSTRUCTION | 0.78 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Balance portion of LDS at Sapkhali PWSS under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in Bishnupur-I Block within South 24-Pgs. W/S Divn.-I, P.H.E. Dte., South 24-Pgs. Dist. [Scheme code: SM/11781][2nd call] | AE SWSD-II | JE4 | ORD/000724/2023-2024 | 398/SWD-I | 18/01/2024 | 02/02/2024 | T.T. ENTERPRISE (PANIHATI) | 7.77 | 7.73 | 99.48 | 99
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Sapkhali Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11781] | Assistant Engineer -II | Junior Engineer | ORD/003021/2023-2024 | 267-AE-II-SMD | 12/03/2024 | 27/03/2024 | AHALYA ENGINEERING WORKS | 0.88 | 0.82 | 92.46 | 100
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SAPHKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11781 | Augmentation | Payment of Quotation for new service connection at Sapkhali PWSS PH No-2 under Bishnupur-I Block. Application No- 1008259620 Reference ID- 106862354 |  |  | BILL/00260/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.36 | 0 | 0 | 0
Total | [13 empty] | 401.77 | 145.57 | 36.23