## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Preparation and submission of Detailed Project Report of CHAK NURSHIKDAR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000229/2021-2022 | 1978/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.55 | 2.55 | 100 | 100
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chak Nursikdarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000442/2022-2023 | 67/SMD | 11/01/2023 | 11/04/2023 | M/S. PS & ASSOCIATES | 25.93 | 12.77 | 49.25 | 50
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for CHAK NURSHIKDAR Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11782] | AE SWSD-II | JE1 | ORD/000231/2022-2023 | 1681/SWD-I | 01/11/2022 | 01/12/2022 | KUNTAL CHOWDHURY | 14.89 | 14.51 | 97.46 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of CHAK NURSHIKDAR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11782) | AE SWSD-II | JE1 | ORD/000441/2022-2023 | 2660/SWD-I | 18/01/2023 | 19/03/2023 | M/S. TORSA ENTERPRISE | 6.04 | 6 | 99.37 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 2555/SWD-I | 09/01/2023 | 09/01/2023 | Resource Division | 5.33 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 32.32 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00023/2023-2024 | BP-2023-24-40 | 18/05/2023 | 18/05/2023 | WBSEDCL | 3.66 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based CHAK NURSHIKDAR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 865 nos.] | AE SWSD-II | JE1 | ORD/000415/2022-2023 | 2469/SWD_I | 30/12/2022 | 30/03/2023 | SANJUKTA ENGINEERS. | 138.64 | 91.85 | 66.25 | 92
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/12/2023 to 31/05/2024) [Vehicle No- WB-11D-3607] | AE SWSD-II | JE4 | ORD/000674/2023-2024 | 2999/SWD-I | 29/11/2023 | 30/05/2024 | AHMED REZA | 0.87 | 2.4 | 275.86 | 90
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2024 to 30/11/2024) [Vehicle NoWB-11D-3607] | AE SWSD-II | JE4 | ORD/000220/2024-2025 | 2449/SWD-I | 24/05/2024 | 23/11/2024 | AHMED REZA | 0.87 | 2.4 | 275.83 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023) | AE SWSD-II |  | ORD/000181/2023-2024 | 773/SWD-I | 31/05/2023 | 30/11/2023 | AHMED REZA | 0.87 | 2.39 | 274.94 | 30
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Improvement of working ambience by providing requsite external luminaires, supplying of chair & table etc. at P.H. No. 1 under Chak Nursikdarpur Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I) (SM/11782) | Assistant Engineer -II | Junior Engineer | ORD/002511/2023-2024 | 210-AE-II-SMD | 28/02/2024 | 14/03/2024 | S.R. CONCERN | 0.75 | 0.75 | 100 | 100
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 01/12/2025 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Construction of boundary wall, approach road, pump hopuse, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for CHAK NURSIKDER PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11782] | AE SWSD-II | JE1 | ORD/000246/2024-2025 | 2666/SWD-I | 07/06/2024 | 16/10/2025 | SRIJON ENTERPRISE | 71.67 | 0 | 0 | 50
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/12/2024 to 31/05/2025) [Vehicle NoWB-11D-3607] | AE SWSD-II | JE4 | ORD/001061/2024-2025 | 4878/SWD-I | 29/11/2024 | 30/05/2025 | AHMED REZA | 0.86 | 2.4 | 277.47 | 1
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Providing protection work of drum sheet walling along with other allied works for the construction of the Boundary Wall at 1st Tubewell site of Chak Nurshikdar PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division-I, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District [SM/11782] | AE S24D1 | JE1 | ORD/000003/2025-2026 | 906/SWD-I | 02/04/2025 | 02/05/2025 | CONCORD PROJECTS PRIVATE LIMITED | 3.33 | 0 | 0 | 75
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHAK NURSHIKDAR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas dis | SM/11782 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for CHAK NURSHIKDAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011738] | AE SWSD-II | JE1 | ORD/000592/2022-2023 | 3112/SWD-I | 24/02/2023 | 20/02/2025 | DEBASHIS DAS | 15.87 | 12.37 | 77.95 | 98
Total | [13 empty] | 429.91 | 150.39 | 34.98