## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for SALPUKURIA Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11783] | AE SWSD-II | JE1 | ORD/000178/2022-2023 | 1453/SWD-I | 26/09/2022 | 26/10/2022 | DIPALI CONSTRUCTION | 14.26 | 0 | 0 | 5
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based SALPUKURIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 910 nos.] | AE SWSD-II | JE1 | ORD/000416/2022-2023 | 2470/SWDI | 30/12/2022 | 30/03/2023 | BHASKAR MONDAL | 179.64 | 109.96 | 61.21 | 90
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Preparation and submission of Detailed Project Report of SALPUKURIA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000226/2021-2022 | 1971/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.69 | 2.65 | 98.68 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SALPUKURIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011734] | AE SWSD-II | JE1 | ORD/000520/2022-2023 | 2910/SWD-I | 14/02/2023 | 01/03/2023 | DIPALI CONSTRUCTION | 1.57 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of SALPUKURIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11783) | AE SWSD-II | JE1 | ORD/000429/2022-2023 | 2574/SWD-I | 10/01/2023 | 11/03/2023 | LAKSHMI IRON | 6.04 | 0 | 0 | 87
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Salpukuria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000506/2022-2023 | 341/SMD | 08/02/2023 | 09/05/2023 | STANDARD ENGINEERING | 25.69 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/05/2023 to 30/09/2023) | AE SWSD-II |  | ORD/000180/2023-2024 | 333/SWD-I | 25/04/2023 | 25/09/2023 | NIRMAL UDYOG | 0.73 | 1.95 | 268.59 | 30
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 15/08/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/10/2023 to 29/02/2024) | AE SWSD-II | JE4 | ORD/000623/2023-2024 | 2388/SWD-I | 27/09/2023 | 26/02/2024 | NIRMAL UDYOG | 0.72 | 1.54 | 213.3 | 99
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for SALPUKURIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011734] | AE SWSD-II | JE1 | ORD/000593/2022-2023 | 3113/SWD-I | 24/02/2023 | 26/03/2023 | DEBASHIS DAS | 15.87 | 15.76 | 99.33 | 98
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 2555/SWD-I | 09/01/2023 | 09/01/2023 | Resource Division | 5.61 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 23.31 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell for SALPUKURIA Piped Water Supply Scheme in BISHNUPUR-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/11783] | AE SWSD-II | JE1 | ORD/000789/2023-2024 | 1072/SWD-I | 04/03/2024 | 30/11/2024 | MONDAL TUBEWELL | 15.9 | 0 | 0 | 98
14 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/03/2024 to 31/08/2024) [Vehhicle No - WB-19J-3488] | AE SWSD-II | JE4 | ORD/000909/2023-2024 | 917/SWD-I | 21/02/2024 | 23/08/2024 | NIRMAL UDYOG | 0.87 | 2.23 | 254.9 | 70
15 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Construction of boundary wall, approach road, Pump house, laying of additional pipeline and other allied works for SALPUKURIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11783] | AE SWSD-II | JE1 | ORD/000249/2024-2025 | 2669/SWD-I | 07/06/2024 | 22/07/2024 | BHASKAR MONDAL | 72.69 | 0 | 0 | 5
16 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/09/2024 to 28/02/2025) [Vehhicle No - WB-19J-3488] | AE SWSD-II | JE4 | ORD/001063/2024-2025 | 3766/SWD-I | 28/08/2024 | 25/02/2025 | NIRMAL UDYOG | 0.86 | 2.18 | 254.07 | 70
17 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Land Development at Salpukuria Piped Water Supply Scheme for 1st Tubewell site in the Arsenic affected areas of South 24-Parganas Water Supply Division-I, PHE Dte. (SM/11783) | AE SWSD-II | JE1 | ORD/000749/2023-2024 | 525/SWD-I | 29/01/2024 | 13/02/2024 | KALAM ENTERPRISE | 3.35 | 3.29 | 98.31 | 99
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04617/2023-2024 | BP-2023-24-478 | 02/02/2024 | 02/02/2024 | WBSEDCL | 3.44 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/03/2025 to 31/08/2025) [Vehhicle No - WB-19J-3488] | AE SWSD-II | JE4 | ORD/001204/2024-2025 | 581/SWD-I | 25/02/2025 | 28/08/2025 | NIRMAL UDYOG | 0.87 | 0.75 | 86.1 | 0
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based SALPUKURIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district | SM/11783 | Augmentation | Payment of quotation for new service connection at Salpukuria PWSS, PH No-2 under Bishnupur-I Block. Application No- 1008270335 Reference Id- 106862719 Quotation Date-13/12/2024 Memo No- 1008270335/Quot/03 |  |  | BILL/02485/2024-2025 | BP-2024-25-540 | 24/01/2025 | 24/01/2025 | WBSEDCL | 16.94 | 0 | 0 | 0
Total | [13 empty] | 496.51 | 140.32 | 28.26