## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Charaghata of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD |  | ORD/000377/2022-2023 | 2211/SWD-I | 13/12/2022 | 11/02/2023 | KHAN ENTERPRISE | 11.52 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Charaghata water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000569/2022-2023 | 588/SMD | 24/02/2023 | 25/05/2023 | SAIKAT ENTERPRISE | 22.37 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Preparation and submission of Detailed Project Report of CHARAGHATA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000449/2021-2022 | 1961/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.74 | 99.39 | 100
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 142.64 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Restoration of Irrigation embankment road for Ground water based CHARAGHATA Piped Water Based Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns. W/S Division-I, P.H.E Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/11787) | AE BSD | JE-1 | ORD/000795/2023-2024 | 1143/SWD-I | 07/03/2024 | 06/04/2024 | L.N. ENTERPRISE | 24.27 | 24.1 | 99.3 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Balance work for laying distribution system, at CHARAGHATA PWSS of JOYNAGAR-I Block, for implementation of surface water based W/S scheme in the arsenic affected areas of South 24-Parganas district under Baruipur Sub-Division of South 24-Pgns, W/S Division-I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000819/2023-2024 | 1136/SWD-I | 06/03/2024 | 05/05/2024 | PATH MAKERS | 34.21 | 29.09 | 85.02 | 100
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/05024/2023-2024 | BP-2023-24-569 | 12/03/2024 | 12/03/2024 | WBSEDCL | 4.96 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Road restoration of L023- Shyamnagar F.P. School to Purba Gobindapur PWD Road |  |  | BILL/01783/2024-2025 | BP-2024-25-808 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 14.73 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHARAGHATA Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1857) | AE BSD | JE RWS,JE-2 | ORD/000273/2022-2023 | 1806/SWD-I | 09/11/2022 | 27/04/2025 | PATH MAKERS | 485.76 | 472.21 | 97.21 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Sinking of 01 no. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHARAGHATA Piped Water Supply Scheme to accommodate FHTC in JOYNAGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11787] |  |  | ORD/001123/2024-2025 | 157/SWD-I | 15/01/2025 | 14/02/2025 | ANCHAR ALI GHORAMI | 19.11 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11787 | Augmentation | Sinking of 01 (one) Rig bored 250mm x 150 mm dia. & 360 mtr. deep Tubewell having 66 mtr housing by Rotary method at Headwork site for CHARAGHATA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. ( SM/11787 ) | AE BSD | JE RWS | ORD/000812/2024-2025 | 4864/SWD-I | 28/11/2024 | 11/02/2025 | SIMPLEX DRILLING COMPANY | 19.02 | 4.65 | 24.47 | 100
Total | [13 empty] | 781.34 | 532.79 | 68.19