## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Preparation and submission of Detailed Project Report of "KRISHNARAMPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000396/2022-2023 | 464/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.62 | 2.62 | 100 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KRISHNARAMPUR Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11789] | AE SWSD-II | JE4 | ORD/000229/2022-2023 | 1680/SWD-I | 01/11/2022 | 01/12/2022 | M/S PURE RENOVATION CONSTRUCTION GROUP | 14.85 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KRISHNARAMPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011787] | AE SWSD-II | JE4 | ORD/000516/2022-2023 | 2908/SWD-I | 14/02/2023 | 01/03/2023 | M/S PURE RENOVATION CONSTRUCTION GROUP (EMAIL ID-SAJIDMOLLA93@GMAIL.COM) | 1.57 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for KRISHNARAMPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011787] | AE SWSD-II | JE4 | ORD/000586/2022-2023 | 3107/SWD-I | 24/02/2023 | 26/03/2023 | MOULI CONSTRUCTION | 15.88 | 15.62 | 98.37 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KRISHNARAMPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11789) (3rd Call) | AE SWSD-II |  | ORD/000252/2023-2024 | 1499/SWD-I | 20/07/2023 | 18/09/2023 | S.P. ENTERPRISE | 6.05 | 5.88 | 97.18 | 100
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 2555/SWD-I | 09/01/2023 | 09/01/2023 | Resource Division | 5.35 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 30.22 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03515/2023-2024 | BP-2023-24-381 | 20/11/2023 | 20/11/2023 | WBSEDCL | 3.59 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KRISHNARAMPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 868 nos.] | AE SWSD-II | JE4 | ORD/000419/2022-2023 | 2473/SWD-I | 30/12/2022 | 30/03/2023 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 157.64 | 139.21 | 88.3 | 98
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 16/11/2025 | CONCORD PROJECTS PVT. LTD. | 106.79 | 30.08 | 28.17 | 20
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Krishnarampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000488/2022-2023 | 246/SMD | 27/01/2023 | 01/01/2026 | T.S. CONSTRUCTION | 25.93 | 12.36 | 47.65 | 85
12 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KRISHNARAMPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas distr | SM/11789 | Augmentation | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Krishnarampur PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11789) | AE SWSD-II | JE4 | ORD/000255/2024-2025 | 2672/SWD-I | 07/06/2024 | 11/10/2025 | NIKHIL SAMADDAR | 50.05 | 0 | 0 | 30
Total | [13 empty] | 420.54 | 205.76 | 48.93