## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Mograhat-1/IV at Hijalghat Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. | SM/11972 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 322/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 38.87 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Providing 100% FHTC in Mograhat-1/IV at Hijalghat Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. | SM/11972 | Augmentation | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall and Laying Distribution System including FHTC for Augmentation of Laying Distribution System to extend benefit off 100% household in Zone-IV at HIJALHAT under Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 6310] [TSM/015076] | AE SWSD-II | JE4 | ORD/000125/2023-2024 | 568/SWD-I | 15/05/2023 | 27/04/2026 | M/S GHOSH AND CO. | 1160.71 | 0 | 0 | 56
Total | [13 empty] | 1199.58 | 0 | 0