## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Preparation and submission of Detailed Project Report of "JALILPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000401/2022-2023 | 461/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.44 | 2.42 | 99.27 | 100
2 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig Ground bored 150mm x 100 mm dia. & 300 mtr. deep Tubewell by Rotary method for JALILPUR PWSS of BISHNUPUR-I Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. | AE SWSD-II | JE2 | ORD/000166/2022-2023 | 1345/SWD-I | 19/09/2022 | 19/10/2022 | ANANTA KUMAR GIRI | 9.65 | 8.83 | 91.47 | 100
3 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Electricity Bills |  |  | BILL/00262/2022-2023 | BP-2022-23-402 | 20/01/2023 |  | WBSEDCL | 3.41 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 3249/SWD-I | 01/03/2023 |  | Resource Division | 16.97 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Restoration charges on Amtala Baruipur Road due to laying of HDPE of 50% of estimate value i.e. 4357850 x 50% = 217893 as per minutes of meeting with Hon'ble MIC. |  |  | BILL/00289/2022-2023 | BP-2022-23-223 | 09/03/2023 |  | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 2.18 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig bored 150mm x 100mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for JALILPUR PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Divn-I, P.H.E. Dte. [TSM/011226][2nd Call] | AE SWSD-II | JE2 | ORD/000687/2022-2023 | 3486/SWD-I | 15/03/2023 | 14/04/2023 | MD. IFTIKAR HASAN | 10.6 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jalilpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000281/2022-2023 | 151/SMD | 16/01/2023 | 16/04/2023 | AHALYA ENGINEERING WORKS | 23.87 | 11.57 | 48.44 | 60
8 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Supply & delivery of standby submersible pumping machinery at PH-1 of Jalilpur w/s Scheme under south 24 pgs Mechanical Division, PHE Dte.( Block-Bishnupur-I) |  |  | ORD/002505/2022-2023 | ..296/AE-II/SMD | 20/03/2023 | 04/04/2023 | AHALYA ENGINEERING WORKS | 0.54 | 0.27 | 50 | 100
9 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 1583/SWD-I | 17/10/2022 |  | Resource Division | 3.34 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed JALILPUR PWSS in Arsenic affected areas of South 24 Pgs. Dist in BISHNUPUR-I Block, under South 24 Pgs W/S Division - I, PHE Dte. | AE SWSD-II | JE2 | ORD/000168/2022-2023 | 1346/SWD-I | 19/09/2022 | 18/11/2022 | GROWING CONCERN | 53.19 | 41.99 | 78.95 | 91
11 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for JALILPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, Dist.-South 24-Pgns. | AE SWSD-II | JE2 | ORD/000326/2022-2023 | 2026/SWD-I | 29/11/2022 | 28/01/2023 | MONDAL PRECISION PVT. LTD. | 122.11 | 109.9 | 90 | 90
12 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at second tubewell site for JALILPUR Piped Water Supply Scheme OF BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011226] | AE SWSD-II | JE2 | ORD/000202/2023-2024 | 1386/SWD-I | 12/07/2023 | 11/08/2023 | MONA CONSTRUCTION | 15.87 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Providing Additional FHTC, C.C base of existing and new FHTC and restoration of damaged concrete road at JALILPUR PWSS in Arsenic affected areas of South 24 pargans District in Bishnupur-I Block, under South 24 pgs W/S Division-I, P.H.E Dte. (New FHTC =60 nos) [Scheme Code: SM/11988] | AE SWSD-II | JE2 | ORD/000545/2023-2024 | 2493/SWD-I | 06/10/2023 | 05/11/2023 | S.P. ENTERPRISE | 6.99 | 4.37 | 62.6 | 80
14 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 09/12/2023 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 15
15 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Construction of Boundary Wall and Pump House at 2nd tubewell site for JALILPUR PWSS of BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II | JE2 | ORD/000518/2024-2025 | 3981/SWD-I | 11/09/2024 | 10/11/2024 | S. DAS ENTERPRISE | 12.61 | 0 | 0 | 0
16 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Laying additional pipeline of distribution system with laying of rising main from 2nd tubewell site for JALILPUR PWSS to accommondate FHTC in BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II | JE2 | ORD/000512/2024-2025 | 3980/SWD-I | 11/09/2024 | 11/10/2024 | S.P. ENTERPRISE | 13.77 | 0 | 0 | 0
17 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Improvement of external illumination arrangement with other allied works at P.H. No. 1 under Jalilpur Water Supply Scheme, South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I)(SM/11988) | Assistant Engineer -II | Junior Engineer | ORD/002455/2023-2024 | 207-AE-II-SMD | 28/02/2024 | 14/03/2024 | PS & ASSOCIATES | 0.75 | 0 | 0 | 100
Total | [13 empty] | 403.77 | 179.35 | 44.42