## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig Ground bored 150mm x 100 mm dia. & 300 mtr. deep Tubewell by Rotary method for JALILPUR PWSS of BISHNUPUR-I Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. | AE SWSD-II | JE2 | ORD/000166/2022-2023 | 1345/SWD-I | 19/09/2022 | 19/10/2022 | ANANTA KUMAR GIRI | 9.65 | 8.83 | 91.47 | 100
2 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Preparation and submission of Detailed Project Report of "JALILPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000401/2022-2023 | 461/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.44 | 2.42 | 99.27 | 100
3 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jalilpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000281/2022-2023 | 151/SMD | 16/01/2023 | 16/04/2023 | AHALYA ENGINEERING WORKS | 23.87 | 11.57 | 48.44 | 60
4 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig bored 150mm x 100mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for JALILPUR PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Divn-I, P.H.E. Dte. [TSM/011226][2nd Call] | AE SWSD-II | JE2 | ORD/000687/2022-2023 | 3486/SWD-I | 15/03/2023 | 14/04/2023 | MD. IFTIKAR HASAN | 10.6 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Supply & delivery of standby submersible pumping machinery at PH-1 of Jalilpur w/s Scheme under south 24 pgs Mechanical Division, PHE Dte.( Block-Bishnupur-I) |  |  | ORD/002505/2022-2023 | ..296/AE-II/SMD | 20/03/2023 | 04/04/2023 | AHALYA ENGINEERING WORKS | 0.54 | 0.54 | 100 | 100
6 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 1583/SWD-I | 17/10/2022 | 17/10/2022 | Resource Division | 3.34 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 16.97 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Restoration charges on Amtala Baruipur Road due to laying of HDPE of 50% of estimate value i.e. 4357850 x 50% = 217893 as per minutes of meeting with Hon'ble MIC. |  |  | BILL/00289/2022-2023 | BP-2022-23-223 | 09/03/2023 | 09/03/2023 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 2.18 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Electricity Bills |  |  | BILL/00262/2022-2023 | BP-2022-23-402 | 20/01/2023 | 20/01/2023 | WBSEDCL | 3.41 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at second tubewell site for JALILPUR Piped Water Supply Scheme OF BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011226] | AE SWSD-II | JE2 | ORD/000202/2023-2024 | 1386/SWD-I | 12/07/2023 | 11/08/2023 | MONA CONSTRUCTION | 15.87 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Improvement of external illumination arrangement with other allied works at P.H. No. 1 under Jalilpur Water Supply Scheme, South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I)(SM/11988) | Assistant Engineer -II | Junior Engineer | ORD/002455/2023-2024 | 207-AE-II-SMD | 28/02/2024 | 14/03/2024 | PS & ASSOCIATES | 0.75 | 0.75 | 100 | 100
12 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Payment for Initial 50% Amount of the Estimated cost Rs. 1791575.00 (Seventeen Lakh Ninety One Thousand Five Hundred Seventy Five Only) i.e Rs. 895788.00 ( Eight Lakh Ninty Five Thousand Seven Hundred Eighty Eight only). Towards Road Restoration work for damages due to Laying of HDPE pipe line near Chainage 6.300 kmp to 7.300kmp of Amtala Baruipur road in the district of s24 parganas under ground water based Jalilpur PWSS to accommodate FHTC in Bishnupur I block under SWD-I PHE.Dte (TSM/011226,SM/11988) |  |  | BILL/00652/2024-2025 | BP-2024-25-364 | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 8.96 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Payment of Quotation for new service connection at Jalilpur PWSS PH No- 2 under Bishnupur-I Block. Application No- 1008249626 Application Date- 09-12-2024 Reference ID- 106856015 Memo No- 1008249626/Quot/03 |  |  | BILL/02237/2024-2025 | BP-2024-25-509 | 19/12/2024 | 19/12/2024 | WBSEDCL | 3.65 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 1st Tube well site for Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs Mechanical Division, PHE Dte. South 24 Parganas District. [SM/11988] | Assistant Engineer -II | Junior Engineer | ORD/001296/2024-2025 | 365/SMD | 06/02/2025 | 07/04/2025 | PADMA ENGINEERING CO. | 0 | 0 | NAN | 0
15 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for JALILPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, Dist.-South 24-Pgns. | AE SWSD-II | JE2 | ORD/000326/2022-2023 | 2026/SWD-I | 29/11/2022 | 11/11/2025 | MONDAL PRECISION PVT. LTD. | 122.11 | 109.9 | 90 | 90
16 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 19/03/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
17 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed JALILPUR PWSS in Arsenic affected areas of South 24 Pgs. Dist in BISHNUPUR-I Block, under South 24 Pgs W/S Division - I, PHE Dte. | AE SWSD-II | JE2 | ORD/000168/2022-2023 | 1346/SWD-I | 19/09/2022 | 01/06/2025 | GROWING CONCERN | 53.19 | 41.99 | 78.95 | 99
18 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Laying additional pipeline of distribution system with laying of rising main from 2nd tubewell site for JALILPUR PWSS to accommondate FHTC in BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II | JE2 | ORD/000512/2024-2025 | 3980/SWD-I | 11/09/2024 | 11/10/2024 | S.P. ENTERPRISE | 13.77 | 1.44 | 10.49 | 80
19 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Construction of Boundary Wall and Pump House at 2nd tubewell site for JALILPUR PWSS of BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II | JE2 | ORD/000518/2024-2025 | 3981/SWD-I | 11/09/2024 | 10/11/2024 | S. DAS ENTERPRISE | 12.61 | 0 | 0 | 1
20 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd tubewell site for JALILPUR Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11988] | AE SWSD-II | JE2 | ORD/000669/2024-2025 | 4442/SWD-I | 28/10/2024 | 27/11/2024 | RAJKUMAR MONDAL | 15.9 | 0 | 0 | 90
21 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs W/S Division-I, South 24 Parganas District. | SM/11988 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 1st Tube well site for Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs Mechanical Division, PHE Dte. South 24 Parganas District. [SM/11988] | Assistant Engineer -II | Junior Engineer | ORD/001294/2024-2025 | 372/SMD | 06/02/2025 | 07/04/2025 | PADMA ENGINEERING CO. | 16.35 | 0 | 0 | 100
Total | [13 empty] | 441.65 | 177.45 | 40.18