## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 47.08 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Material Requisition To Resource Division |  |  | RTOR000247/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 13.89 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01110/2023-2024 | BP-2023-24-155 | 24/07/2023 | 24/07/2023 | WBSEDCL | 4.18 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for KASHINATHPUR piped water supply scheme at headwork site (Dag No. 1562, Khatian No. 2581, JL. No. 115, Mouza- Kashinathpur) & 2nd Tubewell site (Dag No. 1300, Khatian No. 1361 , JL No. 115, Mouza- Kashinathpur), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I | JE-4 | ORD/000171/2022-2023 | 1442/SWD-I | 26/09/2022 | 26/10/2022 | ABU TALEB MONDAL | 28.51 | 0 | 0 | 50
5 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KASHINATHPUR PWSS at headwork site (Dag No. 1562, Khatian No. 2581, JL. No. 115, Mouza- Kashinathpur) & 2nd Tube-well site (Dag No. 1300 Khatian No. 1361, JL No. 115, Mouza- Kashinathpur) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12016] | AE HQ-I | JE-4 | ORD/000737/2022-2023 | 3567/SWD-I | 22/03/2023 | 06/04/2023 | ABUTALEB MONDAL | 3.13 | 0 | 0 | 50
6 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of KASHINATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12016) |  |  | ORD/000565/2024-2025 | 4238/SWD-I | 30/09/2024 | 29/11/2024 | SAMSUL ENTERPRISE | 89.07 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kashinathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000498/2022-2023 | 316/SMD | 06/02/2023 | 06/07/2025 | B.T.PROJECTS PVT.LTD. | 22.86 | 10.5 | 45.95 | 70
8 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Kashinathpur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2255] | AE HQ-I | JE-4 | ORD/000395/2023-2024 | 1878/SWD-I | 18/08/2023 | 13/06/2024 | SAMSUL ENTERPRISE | 486.03 | 141.11 | 29.03 | 40
9 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for KASHINATHPUR Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12016] | AE HQ-I | JE-4 | ORD/000709/2024-2025 | 4539/SWD-I | 06/11/2024 | 08/03/2025 | RAJKUMAR MONDAL | 15.9 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Improvement of outdoor illumination arrangement with allied works at Kashinathpur, PH-1 under Bhangar-I Block water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000544/2024-2025 | 829/SMSD | 12/06/2024 | 27/06/2024 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Supply & Fixing main switch & Bus bar at Pump House no-1 of Kashinathpur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/12016) | Assistant Engineer | Junior Engineer | ORD/002406/2024-2025 | 985/SMSD | 09/07/2024 | 24/07/2024 | B.T.PROJECTS PVT.LTD. | 0.29 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | KASHINATHPUR Pipes Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12016 | New | Quotation for new service(power) connection at Kashinathpur PH-2 Water supply scheme under Bhangar-I Block Reference ID-107057385 Application Nos-1008567456. |  |  | BILL/00674/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 7.23 | 0 | 0 | 0
Total | [13 empty] | 719.07 | 151.62 | 21.09