## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 46.1 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 16.87 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for NAORA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2739] | AE HQ-I | JE-4 | ORD/000430/2023-2024 | 2004/SWD-I | 28/08/2023 | 23/06/2024 | M/S SALIM CONSTRUCTION | 501.09 | 195.67 | 39.05 | 35
4 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of NAORA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12017) |  |  | ORD/000558/2024-2025 | 4231/SWD-I | 30/09/2024 | 29/11/2024 | M/S SALIM CONSTRUCTION | 93.92 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for NAORA piped water supply scheme at headwork site (Dag No. 140, Khatian No. 586, JL. No. 130, Mouza- Kandia) & 2nd Tubewell site (Dag No. 152,160,161,166 & 174 Khatian No. 1320, JL No. 130, Mouza- Kandia), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,AE HQ-II | JE-4 | ORD/000172/2022-2023 | 1443/SWD-I | 26/09/2022 | 26/10/2022 | MUNNA AGROTECH ENTERPRISE | 28.51 | 21.87 | 76.72 | 100
6 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for NAORA PWSS at headwork site (Dag No. 140, Khatian No. 586, JL. No. 130, Mouza- Kandia) & 2nd Tubewell site (Dag No. 152, 160, 161, 166 & 174 Khatian No. 1320, JL No. 130, Mouza- Kandia) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12017] | AE HQ-I,AE HQ-II | JE-4 | ORD/000488/2022-2023 | 2808/SWD-I | 02/02/2023 | 17/02/2023 | MUNNA AGROTECH ENTERPRISE | 3.13 | 3.04 | 96.84 | 100
7 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.39] |  |  | BILL/00469/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 27.93 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Quotation for new power(service) connection at Naora PH-2 Water Supply Scheme under Bhangar- I Block Reference ID-106663973, Application No- 1007921578. |  |  | BILL/01465/2024-2025 | BP-2024-25-351 | 06/09/2024 | 06/09/2024 | WBSEDCL | 17.9 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Quotation for new service (power) connection at Nowra PH-1 , Water supply scheme under Bhangar-I Block. Reference ID-106663979, Application No- 1007921564 |  |  | BILL/01467/2024-2025 | BP-2024-25-352 | 09/09/2024 | 09/09/2024 | WBSEDCL | 4.91 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.42] |  |  | BILL/00472/2024-2025 | BP-2024-25-293 | 11/09/2024 | 11/09/2024 | WBSRDA SOUTH 24 PGS ALIPORE | 31.04 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | NAORA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs. under JJM | SM/12017 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Naora water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000440/2022-2023 | 230/SMD | 24/01/2023 | 01/01/2026 | B.T.PROJECTS PVT.LTD. | 23 | 0 | 0 | 30
Total | [13 empty] | 794.42 | 220.58 | 27.77