## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDANESWAR piped water supply scheme at headwork site (Dag No. 514, Khatian No. 1673, 1674, JL. No. 117, Mouza- Bausahar) & 2nd Tubewell site (Dag No. 1003, Khatian No. 1322, JL No. 117, Mouza- Bausahar), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I |  | ORD/000165/2022-2023 | 1440/SWD-I | 26/09/2022 | 26/10/2022 | ABU TALEB MONDAL | 28.51 | 14.12 | 49.54 | 50
2 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDANESWAR PWSS at headwork site (Dag No. 514, Khatian No. 1673 & 1674 JL. No. 117, Mouza- Bausahar) & 2nd Tubewell site (Dag No. 1003 Khatian No. 1322, JL No. 117, Mouza- Bausahar) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12044] | AE HQ-I |  | ORD/000728/2022-2023 | 3570/SWD-I | 22/03/2023 | 06/04/2023 | ABUTALEB MONDAL | 3.13 | 1.57 | 50 | 50
3 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 1007/SWD- I | 09/06/2023 | 09/06/2023 | Resource Division | 15.39 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 287/SWD-I | 24/04/2023 | 24/04/2023 | Resource Division | 7.08 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00386/2023-2024 | BP-2023-24-60 | 09/06/2023 | 09/06/2023 | WBSEDCL | 4.13 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandaneswar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000496/2022-2023 | 298/SMD | 03/02/2023 | 04/05/2023 | WEST BENGAL ENGINEERING CO. | 22.37 | 10.81 | 48.32 | 97
7 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Improvement of outdoor illumination arrangement with allied works at Chandaneswar PH-1 under Bhangar-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002645/2023-2024 | 259/SMSD | 23/02/2024 | 09/03/2024 | WEST BENGAL ENGINEERING CO. | 0.89 | 0.89 | 100 | 100
8 | SOUTH 24 PARGANAS | Bhangar-I | S24 Pgns Mechanical | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Shifting of HT Line along with DTR at Bausahar(Chandneswar PH-02) Water supply scheme, under Bhangar- I Block |  |  | BILL/01868/2024-2025 | BP-2024-25-472 | 18/11/2024 | 18/11/2024 | WBSEDCL | 2.42 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for CHANDANESWAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2499] | AE HQ-II | JE-4 | ORD/000714/2022-2023 | 3553/SWD-I | 21/03/2023 | 15/01/2024 | TRISHA CONSTRUCTION | 434.18 | 207.88 | 47.88 | 50
10 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of CHANDANESWAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12044) | AE HQ-I | JE-4 | ORD/000560/2024-2025 | 4233/SWD-I | 30/09/2024 | 26/09/2025 | RAKHI CONSTRUCTION | 90.69 | 0 | 0 | 50
11 | SOUTH 24 PARGANAS | Bhangar-I | South 24 Pgs W/S Division I | CHANDANESWAR Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12044 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHANDANESHWAR Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12044] | AE HQ-I | JE-4 | ORD/000708/2024-2025 | 4538/SWD-I | 06/11/2024 | 08/03/2025 | HI-LIGHT ELECTRONICS | 15.9 | 0 | 0 | 100
Total | [13 empty] | 624.7 | 235.27 | 37.66