## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for MATSYAKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/12045] | AE SWSD-II | JE2 | ORD/000232/2022-2023 | 1682/SWD-I | 01/11/2022 | 01/12/2022 | ANIK ENTERPRISE | 14.96 | 0 | 0 | 1
2 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Preparation and submission of Detailed Project Report of "MATSYAKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000398/2022-2023 | 462/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.51 | 2.51 | 99.86 | 100
3 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for MATSYAKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011202] | AE SWSD-II | JE2 | ORD/000509/2022-2023 | 2907/SWD-I | 14/02/2023 | 01/03/2023 | ANIK ENTERPRISE | 1.57 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based MATSYAKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 750 nos.] | AE SWSD-II | JE2 | ORD/000448/2022-2023 | 2686/SWD-I | 20/01/2023 | 20/04/2023 | ULTRA CONSTRUCTION | 101.39 | 76.67 | 75.62 | 60
5 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Matsyakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000508/2022-2023 | 343/SMD | 08/02/2023 | 09/05/2023 | AHALYA ENGINEERING WORKS | 26.58 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 15/08/2026 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 60
7 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of MATSYAKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12045) (3rd Call) | AE SWSD-II |  | ORD/000253/2023-2024 | 1500/SWD-I | 20/07/2023 | 18/09/2023 | RIDIP ENTERPRISE | 6.04 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for MATSYAKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011202] | AE SWSD-II | JE2 | ORD/000590/2022-2023 | 3110/SWD-I | 24/02/2023 | 30/12/2024 | DEBASHIS DAS | 15.86 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 3249/SWD-I | 01/03/2023 | 01/03/2023 | Resource Division | 30.18 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Matshyakhali PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/12045) | AE SWSD-II | JE2 | ORD/000271/2024-2025 | 2921/SWD-I | 25/06/2024 | 09/08/2024 | BHOLANATH CONSTRUCTION (PROPRIETOR) | 91.73 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Bishnupur-I | South 24 Pgs W/S Division I | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Land Development for 1st Tubewell site at MATSYAKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgns Dist. under South 24-Pgns W/S-I, PHE Dte. (SM/12045) | AE SWSD-II | JE2 | ORD/000867/2024-2025 | 4925/SWD-I | 03/12/2024 | 02/01/2025 | SRIJON ENTERPRISE | 32 | 31.89 | 99.64 | 100
12 | SOUTH 24 PARGANAS | Bishnupur-I | S24 Pgns Mechanical | Proposed ground water based MATSYAKHALI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/12045 | New | Payment of Quotation for New Service Connection at Matsyakhali PWSS P.H.No.-1 under Bishnupur-I Block. Application No- 1008438969 Reference ID- 106984474 Memo No- 1008438969/Quot/03, Dt. 11-04-2025 |  |  | BILL/00361/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 10.21 | 0 | 0 | 0
Total | [13 empty] | 438.5 | 111.06 | 25.33