## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000087/2022-2023 | 1199/SWD-I | 02/09/2022 | 02/10/2022 | UMAR ALI KHAN | 20.06 | 18.08 | 90.12 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Preparation and submission of Detailed Project Report of CHANDIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000168/2021-2022 | 1911/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.62 | 2.45 | 93.6 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chandipur PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/012519] | AE BSD |  | ORD/000788/2022-2023 | 3676/SWD-I | 29/03/2023 | 13/04/2023 | UMAR ALI KHAN | 2.2 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Construction of chlorination room at CHANDIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012519] | AE BSD |  | ORD/000126/2022-2023 | 1294/SWD-I | 14/09/2022 | 13/11/2022 | JYOTI ENTERPRISE | 5.46 | 4.28 | 78.27 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000265/2023-2024 | 2416/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 4.06 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01105/2023-2024 | BP-2023-24-154 | 24/07/2023 | 24/07/2023 | WBSEDCL | 2.26 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at CHANDIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [Nos of FHTC- 472] | AE BSD |  | ORD/000096/2022-2023 | 1208/SWD-I | 02/09/2022 | 01/12/2022 | M/S. SUMAN ENTERPRISE | 92.16 | 51.06 | 55.41 | 60
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based Chandipur piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12046) |  |  | ORD/000336/2024-2025 | 3310/SWD-I | 23/07/2024 | 06/09/2024 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 41.61 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000340/2023-2024 | 269/SWD-I | 10/01/2024 | 10/01/2024 | Resource Division | 2.91 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based CHANDIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12046 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Chandipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000452/2022-2023 | 3932/SMD | 30/12/2022 | 01/05/2024 | K.S.P ENTERPRISE | 11.18 | 10.07 | 90.12 | 100
Total | [13 empty] | 184.52 | 85.94 | 46.58