## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KAPINDAPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD |  | ORD/000089/2022-2023 | 1201/SWD-I | 02/09/2022 | 02/10/2022 | BENGAL ENTERPRISE | 20.07 | 19.03 | 94.85 | 100
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Preparation and submission of Detailed Project Report of KAPINDAPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000165/2021-2022 | 1913/SWD-I | 27/01/2022 | 26/02/2022 | ASTER CONSULTANCY | 2.62 | 2.62 | 100 | 100
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Construction of chlorination room at KAPINDAPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012516] | AE BSD |  | ORD/000288/2022-2023 | 1784/SWD-I | 07/11/2022 | 06/01/2023 | M/S. FAIZUL HAQUE BISWAS | 5.75 | 4.75 | 82.62 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Supply & installation of LED board at PH-I of Dadpur Dighirpar & Kapindarpur w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Baruipur] |  |  | ORD/000897/2023-2024 | 1O68/SMSD | 17/08/2023 | 27/08/2023 | DITHI ENTERPRISE | 0.78 | 0.78 | 100 | 100
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 6.89 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Payment of electric bill for new service connection under SMD, PHE Dte. |  |  | BILL/01961/2022-2023 | BP-2022-23-477 | 31/03/2023 | 31/03/2023 | WBSEDCL | 3.17 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based Kapindapur piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12051) |  |  | ORD/000359/2024-2025 | 3459/SWD-I | 02/08/2024 | 16/09/2024 | S R ENTERPRISE (BIRBHUM) | 50.51 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kapindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000277/2022-2023 | 3920/SMD | 30/12/2022 | 30/03/2023 | PERFECT AIRCONDITION | 12.89 | 12.32 | 95.57 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Road Restoration of Madarat More Riksha Stand to Najirpur Auto Stand via Kobindapur More to Vurkul Khalpar |  |  | BILL/01736/2024-2025 | BP-2024-25-800 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.82 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Ground water based KAPINDAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/12051 | Augmentation | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KAPINDAPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 941) | AE BSD | JE RWS,JE-2 | ORD/000236/2022-2023 | 1711/SWD-I | 02/11/2022 | 30/06/2025 | SAKTI ENTERPRISE | 224.76 | 202.07 | 89.91 | 100
Total | [13 empty] | 330.25 | 241.58 | 73.15